## CMS projects
Task | Owner | Time
Request to be added to a corporate release | Geo Manager
Request CMS Training | Country Manager
Identify Author
Identify Editor
Identify Moderator
Provide Idsid
CMS Training | Corporate Team
Request Channels | Country Manager
Include links and local language for the following
Legal
Privacy
Contact Us
Site Recommendations
Tranlsations for all Tabs
Deliver Resource Identifiers and alt tags
CMS Channel Created | Corporate Team | Time determined by Corporate team
Enter CMS Content | CMS Author
Review and approve CMS pages | CMS Editor/Moderator | parellel with entry weeks 5-14
Review and approve CMS pages | CMS Editors and Moderators
Deliver Word/PDF files for posting to Download server | Country Manager
Submit content in designated QA builds | CMS Author/Corporate Team | Time determined by Corporate team
QA | QA | Time determined by Corporate team
Remain on call for QA Defects | CMS Author/Editor/Moderator | Time determined by Corporate team
Release | Corporate Team | Time determined by Corporate team
On average, process takes approx 4 months