## Overview
Intel® Education Designing Effective Projects
Adaptation Toolkit
Overview
Introduction
The Designing Effective Projects online resource (from the Intel® Education Web site, www.intel.com/education/designprojects), was designed to compliment the Intel® Teach Program core content strands. This material can be used, in whole or in part, to support your teachers as training materials or other support resources. You may use this material in Web format, or make use of it in other resource materials (such as: presentations, manuals, or handouts) that meet your needs. Designing Effective Projects provides a foundation for good planning and supports your teachers in adapting these project-based units or developing their own from scratch. Adaptation for Designing Effective Projects consists of the following steps:
1. Planning
2. Reviewing scripts (Translating scripts if applicable)
3. Integrating local unit plans
4. Loading content into an online system or printing for production
Adaptation Process
Meet with your Regional Web Manager to determine the final format of Designing Effective Projects you will need. Designing Effective Projects can be made available on your Intel Education Web site and/or distributed with curriculum resource CDs. Review the Copyright License Agreement. Then, begin the adaptation process by reviewing the corresponding Checklist.
Contacts
First, contact your Regional Web Manager.
If you have additional questions or need assistance with adaptation, please contact:
Anne Batey (anne.batey@intel.com)
Designing Effective Projects Contents
The Designing Effective Projects resource includes a collection of exemplary Unit Plans that integrate technology into classroom projects. Most of the units were developed by teachers participating in the Intel® Teach professional development program. The program emphasizes curriculum development that aligns to standards and promotes higher-order thinking using Curriculum-Framing Questions, authentic project tasks, effective instructional strategies, and performance assessment. Designing Effective Projects is developed from approximately 3 scripts that emcompasses the surround. Additionally, each unit plan will be a additional script. The scripts are Microsoft Word* documents. The adapted script content is entered into the online MCMS System, reviewed, and finally published to the Intel Education Web site or printed on CD for end users.

## Roles
Intel® Education Designing Effective Projects
Adaptation Toolkit ¦ Overview of Roles
Overview: This worksheet provides a description of the various roles involved in the Intel® Education Designing Effective Projects adaptation. The other tabs provide the adaptation steps in which each role is responsible. Adaptation is not linear. Some of the steps can be done at the same time as other steps.
Role | Description
Education Manager | This is the Intel Education Manager for the country/region.
Regional Web Manager | This is the Regional Education Web Manager for the region
Content Developer(s)/ Adaptor(s) | This role is responsible for adding or updating content for Designing Effective Projects. They will determine the scope of changes, modifications, and oversee all translation requirements. They will coordinate and oversee local unit plans needed. They will revise scripts as needed and prepare all final scripts and screenshots for either content entry into the MCMS system or CD version.
Technical Resource | This role is responsible for uploading the adapted content to the MCMS system or creating the final CD version of the adapted content.
Intel Corporate Team | This is the Intel Corporate Web Team and Intel Corporate K-12 Team Members , including Content, Web, Marketing, and Deployment teams.

## Web Checklist
Please note: Many steps can be completed at the same time.
Target Complete Date | Status | Phase | Owner | Step | Task | Resource
|  | Orientation | Ed Manager |  | Conduct a review of the Corporate Online content to familiarize your team with the content.
|  | Planning | Ed Manager & Regional Web Manager | Step 1 | Meet with your Regional Web Manager to plan for including the Web site in an upcoming Web release. Request the current corporate web release schedule to determine if one of the current scheduled releases will meet your needs to publish the pilot into production from Laurye Clampitt (laurax.m.clampitt@intel.com) Alternative contact: Jennifer Sheldon (jennifer.l.sheldon@intel.com). Propose a release date. Laurye Clampitt (laurax.m.clampitt@intel.com) will then send a proposed QA schedule for your review and coordinate your pilot through the QA and release process. Alternative contact: Jennifer Sheldon (jennifer.l.sheldon@intel.com). Note: Currently, it takes a minimum of four (4) weeks to submit online curriculum through the QA and CCB process to release into production. It is recommended that you add an additional two to three weeks for development efforts.
|  | Planning | Ed Manager & Regional Web Manager | Step 2 | Work with your regional Web/online manager to identify a technical author and editor/moderator (as needed) for adaptation of online content. [In Asia contact Anjali Mallya (anjali.mallya@intel.com), in EMEA contact Danny Arati (danny.arati@intel.com), and in LAR contact Mario Cerdas (mario.a.cerdas@intel.com).] The MCMS is in English so technical team will need to understand and communicate in English.
|  | Planning | Ed Manager | Step 3 | Request the creation of the CMS Channel from Laurye Clampitt (laurax.m.clampitt@intel.com). Alternative contact: Larry Oesterreich (larry.oesterreich@intel.com). | CMS Tasks
|  | Content | Content Developer(s)/ Adaptor(s) | Step 4 | Review, make revisions, and finalize the scripts as needed. Scripts are located on the IE K-12 Designing Effective Projects File Sharing Site (Content and Files tab > Surround) | Capturing Important Terms and Concepts
|  | Content | Content Developer(s)/ Adaptor(s) | Step 5 | Identify sample corporate unit plans from the Web site to adapt or select local unit plans.
|  | Content | Content Developer(s)/ Adaptor(s) | Step 6 | Review, make revisions, and finalize unit plans as needed. | Unit Portfolio Revision Checklist
|  | Content | Content Developer(s)/ Adaptor(s) | Step 7 | Determine if local images in the surround will be used. Identify an image file for each unit plan.
|  | Content | Content Developer(s)/ Adaptor(s) | Step 8 | Decide if you will be linking to web pages for the unit plan supporting documents or linking to the document itself. Also, decide if you will be providing a PDF so users can download the entire unit plan for offline viewing.
|  | Technical | Technical Resource | Step 9 | Load script content into the CMS. If you encounter any problems loading content, please contact Laurye Clampitt, Laurax.m.clampitt@intel.com, for assistance. | CMS Unit Plan Checklist
|  | Content/ Technical | Content Developer(s)/ Adaptor(s) & Technical Resource with Moderator Role (within CMS) | Step 10 | Review to make sure your scripts and the content loaded match. We recommend an independent review. NOTE: It is strongly recommended that you maintain current Word script files that contain all current content.
|  | Web Support | Regional Web Mgr, Ed Manager, and Technical Resource | Step 11 | Optional: Develop a landing page and plan for the release cycle. The Corporate Designing Effective Projects Landing Page is included on the IE K12 Designing Effective Projects File Sharing Site in the Project Design script. You can translate and localize the contents. | Intel Education K-12 DEP File Sharing Site

## Print Checklist
Target Complete Date | Status | Phase | Owner | Step | Task | Resource
|  | Orientation | Ed Manager |  | Conduct a review of the Corporate Online content to familiarize your team with the content.
|  | Planning | Ed Manager & Regional Web Manager | Step 1 | Meet with your Regional Web Manager to plan for including the content on CD version.
|  | Content | Content Developer(s)/ Adaptor(s) | Step 2 | Review, make revisions, and finalize the scripts as needed. IE K-12 Designing Effective Projects File Sharing Site (Content and Files tab > Surround) | Capturing Important Terms and Concepts
|  | Content | Content Developer(s)/ Adaptor(s) | Step 3 | Identify sample corporate unit plans from the Web site to adapt or select local unit plans.
|  | Content | Content Developer(s)/ Adaptor(s) | Step 4 | Review, make revisions, and finalize unit plans as needed. | UnitPortfolio Revision Checklist
|  | Content | Content Developer(s)/ Adaptor(s) | Step 5 | Determine if local images in the surround will be used.
|  | Post-Adaptation | Technical Resource | Step 6 | Put the end user application on CD or a web-based interface as needed.
|  | Post-Adaptation | Technical Resource | Step 7 | QA completed CD, testing every link.