Intel® Teach Program Getting Started Course v.2.0

Curriculum Adaptation

Introduction

This document is designed to help you adapt the curriculum materials for the Intel® Teach Getting Started Course. The intent of this document and (related adaptation documents) is to serve as a guide as you create your own curriculum materials, using the completed curriculum files (language: U.S. English) and provided templates as a model.

It is recommended that you refer to this document prior to and during the development of your Getting Started curriculum.

NOTE: This document only includes information about adapting the Getting Started Course curriculum manuals and certificates. Should you require additional information about adapting the Intel® Education Help Guide (digital version), please see the associated Help Guide Adaptation Toolkit.

Contents of this Document:

- Introduction, Related Documents, and Contacts	Page 1

- Software Requirements	Page 2

- Adaptation Process	Page 2

- Adaptation Timeline (Recommended Model)	Page 4

Related Documents:

- Adaptation FAQ: This document provides answers to frequently asked adaptation questions.

- Complete Curriculum Files (language: U.S. English): The Production Kit CD contains complete production files for the curriculum manual (language: U.S. English). You will be adapting these files (translating and localizing) to create your country’s curriculum.

Contacts:

If you have questions or need assistance with adaptation, please contact Shelley Shott (Shelley.shott@intel.com).

Software Requirements

To create your curriculum, you must meet or exceed the following software requirements:

Mandatory Software Requirements

Adobe Acrobat Reader 5.0* or above is required to: - View the complete curriculum files (language: U.S. English) [PDF versions]

Neo Sans Intel font family in your country’s language (or Intel CBID approved alternative) is required to: - Create your curriculum manuals

Optional Software Requirements

QuarkXPress 5.0* or higher is required to: - View and modify the complete curriculum files (language: U.S. English) Note: If you are using publication software other than QuarkXPress, you will need to recreate the manual formatting in that software.

Adaptation Process

Pre-Production: - Review (and translate if needed) all adaptation documents for the Getting Started v.2.0 curriculum. - Establish your adaptation team and adaptation timeline. - Purchase software for use in adaptation and production (if needed).

Step 1: Adapt (translate and localize) the Intel® Education Help Guide, if a version does not already exist for your country. Refer to the Help Guide Adaptation Toolkit for more information. Refer to the Help Guide File Sharing Site for adaptation information. Note: Version 2.0 of the Getting Started Course curriculum uses the digital version of the Help Guide.

Step 2: Adapt (translate and localize) the Getting Started manual and MT Appendix. Remove all localization notes from the curriculum manual.

Step 3: Choose a cover design for the manual that best meets your needs (from the available template options). Adapt (translate and localize) the manual cover.

Step 4: Review and edit your completed manual.

Step 5: Send a PDF version of your final manual to Shelley Shott at Shelley.shott@intel.com for a high-level review. Make any identified changes to your manual and finalize it.

Step 6: Choose a Certificate of Completion design for MTs and PTs that best meets your needs (from the available template options). Adapt (translate and localize) the certificates.

Step 7: Determine how you will print and distribute your curriculum materials to MTs and PTs. Recommended options include: - Option A: Print one manual for MTs and PTs and then print the MT appendix separate (for distribution to only MTs). - Option B: Print one manual for MTs (which includes the curriculum and MT Appendix) and print a separate manual for PTs (which only includes the curriculum).

Step 8: Print your final files.

Adaptation Timeline (Recommended Model)

This is a model for a recommended timeline/schedule for completing production of the Getting Started curriculum manuals and certificates. Please adapt this timeline to suit your needs and develop your own adaptation and production timeline.

- Assumed resources: 1 full-time production person, 1 part-time editor, and 1 manager to oversee project management aspects part-time

- Acceleration options: This timeline could be shortened if additional resources are available to work on the project. Also, if your country has already adapted the Help Guide, that process step can be bypassed.

|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pre-Production: - Review (and translate, if needed) the adaptation documents - Establish an adaptation team & timeline - Purchase software for use in production (if needed) |  |  |  |  |  |  |  |
| Step 1: Adapt the Help Guide (if needed) |  |  |  |  |  |  |  |
| Step 2: Adapt the manual and MT Appendix |  |  |  |  |  |  |  |
| Step 3: Adapt the manual cover |  |  |  |  |  |  |  |
| Step 4: Review and edit your completed manual |  |  |  |  |  |  |  |
| Step 5: Send PDF version of the manual to Shelley Shott for review. Make any identified changes. |  |  |  |  |  |  |  |
| Step 6: Adapt the MT and PT Certificates of Completion |  |  |  |  |  |  |  |

NOTE: Post-production items are not on this adaptation timeline.

- Printing the materials may take three weeks or longer.

- Distribution time will vary based on the number of participants and locations involved.