Intel® Teach Program

File Sharing Site + Course Update Site

Access | Definitions | Timelines | Process Steps | Maintenance after Launch | Standard Deliverables

Intel® Education has two externally accessible, password-protected Web sites: the File Sharing Site supports Intel Education resource adaptation and the Course Update Site supports Intel® Teach course delivery in the U.S.

Below you’ll find detailed information about the purpose, content team deliverables, and maintenance needs to support your role.

Content Team should have full access to review all courses in each site, and they should have “Course Author” access to the content they are assigned as Course Lead for:

- File Sharing Site - https://teachonline.intel.com/content - you should have access to all courses (when you are identified as a content lead, you’ll also be given ‘Course Author’ role to enable you to edit)

  - Note: The Create Course Environment in the File Sharing Site is provided to support you in your Course Author Role.

- Course Update Site- http://teachonline.intel.com/courseupdates/ - follow instructions on the landing page: you will register and enroll in each course

Definitions

The purpose of the Course Updates site (http://teachonline.intel.com/courseupdates) is (1) to prepare existing users (Senior and Master Level) to deliver a newer version of curriculum than they were certified on and (2) to house the most up-to-date resources (Senior and Master level training resources and CD resources) for trainers to download prior to delivering a course (note: Essentials Online facilitators should only review the course updates site to get a feel for the updates and should use the links to the content in their copy of the course they are delivering to participants.

Audience is certified & authorized MTs (MLs) and STs (SFs)

- Structure is consistent, tabs are: Overview, MT Resources, CD Resources, ST Resources

- Content Team members create this site content for the release of a new course, and keep it updated through revisions.

- Overview content is designed to be viewed electronically or printed for review with the curriculum manual off line.

The purpose of the File Sharing Site (http://teachonline.intel.com/content) is to provide geos (Intel Education Managers and their RTAs / development agencies in other locations, who implement the curriculum and resources) with the curriculum files so they can localize the curriculum for their area. In most cases, we provide:

- All production files (Quark, and/or InDesign, PDFs, imagery, RoboHelp file, CD label, any additional production resources)

- Curriculum “scripts” (Word “content scripts” and for an update also Word docs with tracked changes)

- Supporting resources (agendas, ST/MT presentations, all CD files)

- Adaptation Materials (guidelines, processes, and tips for geos)

- List of all files and materials needed for adaptation

- Structure has some consistency, but varies if curriculum is new or an update, and by delivery (Online, print and/or CD). Content Lead should recommend best format for understanding, based on existing models.

- Content Team members create and maintain this site content for the release of a new course and version updates.

General Delivery Timelines (rough benchmarks; may vary by complexity or demand):

- Course Update Site Overview Course – must be ready when curriculum is shipped. This is typically 2 weeks after course curriculum content has gone to print.

- File Sharing Site Course – 2 weeks after final content delivery

Process Steps

Course Update Site

- Content Lead provides updated agenda as soon as possible (long lead time required to make changes to the intel.com/education Web site), to update http://www.intel.com/education/teach/expansion/inservice2_curriculum.htm

- Content Lead provides document detailing changes from previous version (if applicable) as early as feasible (these are used in communications to the field)

Examples:

- Alison will build ‘shell’ > Content Lead provides content for the pages (suggested timing is during final editing phase), links are added and tables are built.

- Content lead provides File List (subset of FSS File list: this is only for building the CU site, this will not need to be maintained: the FSS file list will be the master) > Alison or Laurye posts final files to Download and provides URLs on the File List (root level or direct) > Content Lead reviews (content + checks all links)

  - File list needs to be maintained on SharePoint (notify Customer Support where to retrieve them)

Example

- For the US, Alison communicates readiness to ITAs, LEAs (comm. from Theresa to STs), MTs with a description of the curriculum update

- Users self register

> Move into maintenance mode (see below)

FSS

- Confirm before project start whether only final files are needed (“clean” Word scripts) or final files + files with tracked changes are required (Shelley Shott / Anne Batey decision)

- Content Lead documents the structure of FSS shortly after determining the curriculum structure. Delivery for a course/resource (print, print + CD, online…) and version (new or update) should be considered when drafting a structure. Review other File Sharing Site courses for ideas.

    - Alison builds ‘frame’ per structure and reviews with Anne/Shelley.

- Content Lead creates File List at the beginning of a project (portions of the File List – Resources for MTs and STs - are used for the Course Updates File List). The File List is updated throughout development, and maintained  in SharePoint after launch as updates are made – example:

- Content Lead provides content for FSS (suggested timing is during final editing phase)

- After final edits, Content Lead adds word counts to File List. (Recommend QuickCount software).

- Content Lead delivers final docs and final File List (upload to SharePoint, using organization planned for FSS / CU) – notifies Alison.elmer@intel.com and Laurye.m.clampitt@intel.com

- Content Lead updates existing (or provides new) adaptation support documentation (Adaptation ‘toolkit’ or guide – any material recommended for geos to use when adapting the materials)

- Alison or Laurye provide URLs in the File List > Content Lead updates File Sharing Site links

- Final review (Content Lead, Anne/Shelley, Alison and Laurye): structure, content, links.

- Shelley communicates readiness to Ed Managers

- All required users are invited (requests go to Julia Fischer,  FSS Registration tracker is updated)

> Move into maintenance mode (see below)

Maintenance after launch

File Sharing Site: Content Lead should update ‘FSS course’ content as needed – for instance if there is a typo or if directions need clarification based on feedback the following are steps that should be taken:

- notify Shelley/Anne of update needed – they determine next steps based on impact to geos, including update to be completed, timing to update File Sharing Site, communication to Geos (e-mail Alison with notice of the update).

- Update SharePoint version - the most recent version should be saved in SharePoint, the File List should be updated,

- Content Lead should send any updated resource (keeping the file name consistent) to Alison and Laurye to post on the download server.

- Any updates to resources that also are provided on the Course Update Site may require additional effort:

  - If the Download URL is unchanged and is already included on the Course Update site, the file will automatically be updated on the Course Update site – no work required

  - If the URL is new, it needs to be added to the Course Update Site

  - If a URL is removed, it also may need to be removed from the Course Update Site

Course Update Site: Content Lead should update content as needed (e-mail Alison with notice of the update). As existing documents are updated, the most recent version should be saved in SharePoint, and the Content Lead should send any updated resource (keeping the file name consistent) to Alison and Laurye to post. Remember that many files are shared by both the Course Update Site and the File Sharing Site: be sure to update the File Sharing Site following the steps above.

- Julia and Customer Support are able to provide survey data upon request. Content Leads may be interested in accessing this data to understand use of their update course.

List of standard deliverables

| Deliverable | Use | FSS | CU | Creation | By | To |
| --- | --- | --- | --- | --- | --- | --- |
| File List | Geos for reference, for development of FS + CU sites | x | X | Throughout the project | Content Lead | Master saved in SharePoint, Posted to FSS – notify Alison and Laurye when final |
| Course Update File Structure | Alison and/or Laurye use for posting to Download Server |  | X | Can pull from File Sharing Site File List | Content Lead | Alison and Laurye |
| Course Overview description doc | Updates to Web site, communications to participants | x | X | As soon as available (required for communications pre launch) | Content Lead | Alison (Anne/Shelley approve) |
| “Clean” Word Scripts | Curriculum, Geos for adaptation | x |  | Throughout the project | Content Team | Master saved in SharePoint, Posted to FSS, flowed into Quark or InDesign |
| Word scripts with tracked changes | Geo who has prior version | X |  | Throughout the project | Content Team (consolidated list) | Master saved in SharePoint, Posted to FSS |
| ST/MT Resources with tracked changes | Geo who has prior version | X |  | Throughout the project | Content Team (consolidated list) | Master saved in SharePoint, Posted to FSS |
| Production Files (Quark / InDesign, Robo Help Files…) | Curriculum, Geos | X |  | After content final (some work done concurrently) | Content Team | Master saved in SharePoint, Posted to FSS |
| MT / ST / CD Resources | Trainers, Geos | X | X | Concurrently | Content Team | Master saved in SharePoint, Posted to FSS |
| Adaptation Resources | Geos | X |  | Concurrently | Content Team | Master saved in SharePoint, Posted to FSS |