## Content Overview
Project Plan: | <Insert Project Name>
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Request participation in a Corporate release
Decide where to host Downloadable Word and PDF files
Download materials from FSS
Request CMS Channel
Translate CMS Variables
Content
Localize and Translate Project Materials
Create additional supporting materials (screen shots, student examples, unit plans, image selection, etc)
Create and submit an Adaptation Plan
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account
Web
Load the content in the CMS
Review and approve the content in the CMS
Post word and pdf files
Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 QA Build 002 QA Build 003 QA Build 004 QA Build 005 QA Build 006 QA Build 007 QA Build 008
Fix defects
Final Production
Launch
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21
Planning | bar: ww1 to ww16
Schedule Project Orientation Meeting | WM | 1 Day | bar: ww1
Request team accounts to File Sharing site | WM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | WM | 1 Day | bar: ww1
Schedule Project Status meetings | WM | 1 Day | bar: ww1
Set Up | bar: ww1 to ww16
Request participation in a Corporate release | WM | 1 Day | bar: ww1
Decide where to host Downloadable Word and PDF files | WM | 1 Day | bar: ww1
Download materials from FSS | RTA | 1 Day | bar: ww1
Request CMS Channel | WM | 1 Day | bar: ww1
Translate CMS Variables | EM/RTA | 1 week | bar: ww2
Content | bar: ww1 to ww16
Create and submit an Adaptation Plan | EM | 1 week | bar: ww2
Create ST Training Plan if applicable | RTA | 1 week | bar: ww3
Localize and Translate Project Materials | RTA | 4 weeks | bar: ww4 to ww7
Create additional supporting materials (screen shots, student examples, unit plans, image selection, etc) | RTA | 1-2 weeks | bar: ww7 to ww8
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww5 to ww8
Edit the content | 2nd ST trainer | cycle | bar: ww6 to ww9
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww7 to ww10
Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account | PT and RTA | 1 Day | bar: ww7
Web
Load the content in the CMS | PT | 5 weeks | bar: ww7 to ww11
Review and approve the content in the CMS | PT | 1 week | bar: ww11
Post word and pdf files | PT | 1 week | bar: ww11
Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 | PT | 1 Day | bar: ww11
QA build 002 | PT | 1 Day | bar: ww12
QA Build 003 | PT | 1 Day | bar: ww12
QA Build 004 | PT | 1 Day | bar: ww13
QA Build 005 | PT | 1 Day | bar: ww13
QA build 006 | PT | 1 Day | bar: ww14
QA Build 007 | PT | 1 Day | bar: ww14
QA Build 008 | PT | 1 Day | bar: ww15
Fix defects | PT | during Builds | bar: ww13 to ww15
Final Production
Launch | Corporate Team | 1 week | bar: ww16
Post Project
Reflect on the Project | EM or WM | 1 week | bar: ww17
Document BKMs | EM or WM | 1 week | bar: ww17
WM=Web Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Web Release Month>
Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date | CMS Entry | Date | Approver | Date