## Content Overview
Project Plan: | Thinking Tools
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Request participation in a Corporate release
Decide where to host Downloadable Word and PDF files
Download materials from FSS
Request CMS Channel
Translate Variables for the CMS and Workspace
Content
Localize and Translate Project Materials
Create and submit an Adaptation Plan
Teacher Workspace launched
Create Teacher Workspace Examples
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account
Web
Load the content in the CMS
Review and approve the content in the CMS
Post word and pdf files
Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 QA Build 002 QA Build 003 QA Build 004 QA Build 005 QA Build 006 QA Build 007 QA Build 008
Fix defects
Final Production
Launch
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21
Planning | bar: ww1 to ww16
Schedule Project Orientation Meeting | WM | 1 Day | bar: ww1
Request team accounts to File Sharing site | WM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | WM | 1 Day | bar: ww1
Schedule Project Status meetings | WM | 1 Day | bar: ww1
Set Up | bar: ww1 to ww16
Request participation in a Corporate release | WM | 1 Day | bar: ww1
Decide where to host Downloadable Word and PDF files | WM | 1 Day | bar: ww1
Download materials from FSS | RTA | 1 Day | bar: ww1
Request CMS Channel | WM | 1 Day | bar: ww1
Translate Variables for the CMS and Workspace | EM/RTA | 1 week | bar: ww2
Content | bar: ww1 to ww16
Localize and Translate Project Materials | RTA | 4 weeks | bar: ww3 to ww6
Create and submit an Adaptation Plan | EM | 1 week | bar: ww6
Teacher Workspace launched | Corporate Team | 1 Day | bar: ww11
Create Teacher Workspace Examples | Teacher | 2 weeks | bar: ww12 to ww13
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww4 to ww7
Edit the content | 2nd ST trainer | cycle | bar: ww5 to ww8
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww6 to ww9
Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account | PT and RTA | 1 Day | bar: ww7
Web
Load the content in the CMS | PT | 5 weeks | bar: ww7 to ww10
Review and approve the content in the CMS | PT | 1 week | bar: ww10
Post word and pdf files | PT | 1 week | bar: ww10
Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 | PT | 1 Day | bar: ww11
QA build 002 | PT | 1 Day | bar: ww12
QA Build 003 | PT | 1 Day | bar: ww12
QA Build 004 | PT | 1 Day | bar: ww13
QA Build 005 | PT | 1 Day | bar: ww13
QA build 006 | PT | 1 Day | bar: ww14
QA Build 007 | PT | 1 Day | bar: ww14
QA Build 008 | PT | 1 Day | bar: ww15
Fix defects | PT | during Builds | bar: ww13 to ww15
Final Production
Launch | Corporate Team | 1 week | bar: ww16; ww20
Post Project
Reflect on the Project | EM or WM | 1 week | bar: ww17; ww21
Document BKMs | EM or WM | 1 week | bar: ww17; ww21
WM=Web Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Web Release Month>
Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date | CMS Entry | Date | Approver | Date