## Content Overview
Project Plan: | <Insert Project Name>
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Obtain a copy of the Curriculum Guidelines Asset DVD
Download materials from FSS
Content
Localize and Translate Project Materials
Create and submit an Adaptation Plan
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Optional: attend a Quark or Robohelp Training
Production
Produce the Manual
Produce a CD
Print Manuals and CD for pilot
Quality Assurance
Conduct a Pilot
Edit the Pilot Content
Integrate the Pilot Revisions
Integrate Final Edits into the Design Templates
Final Production
Print Final Materials
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21
Planning | bar: ww1 to ww16
Schedule Project Orientation Meeting | CM | 1 Day | bar: ww1
Request team accounts to File Sharing site | CM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | CM | 1 Day | bar: ww1
Schedule Project Status meetings | CM | 1 Day | bar: ww1
Set Up | bar: ww1 to ww16
Obtain a copy of the Curriculum Guidelines Asset DVD | EM | 1 Day | bar: ww1
Download materials from FSS | RTA | 1 Day | bar: ww1
Content | bar: ww1 to ww16
Localize and Translate Project Materials | RTA | 4 weeks | bar: ww2 to ww5
Create and submit an Adaptation Plan | EM | 1 week | bar: ww5
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww3 to ww6
Edit the content | 2nd ST trainer | cycle | bar: ww4 to ww7
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww5 to ww8
Training
Optional: attend a Quark or Robohelp Training | PT and RTA | 1 Day | bar: ww5
Production
Produce the Manual | PT | 5 weeks | bar: ww6 to ww9
Produce a CD | PT | 1 week | bar: ww10
Print Manuals and CD for pilot | RTA | 1 week | bar: ww10
Quality Assurance
Conduct a Pilot | EM | 6 weeks | bar: ww11 to ww16
Edit the Pilot Content | RTA | 1 week | bar: ww17
Integrate the Pilot Revisions | PT | 1 week | bar: ww18
Integrate Final Edits into the Design Templates | RTA | 2 weeks | bar: ww19
Final Production
Print Final Materials | RTA | 1 week | bar: ww19 to ww20
Post Project
Reflect on the Project | EM or CM | 1 week | bar: ww21
Document BKMs | EM or CM | 1 week | bar: ww21
CM=CAG Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Project Deadline Date>
Modules/Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date