## Content Overview
Project Plan: | Essentials Online Course
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Note: This project plan includes DEP and AP. If you already have these resources, please delete the steps in this plan.
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Obtain a copy of the Curriculum Guidelines Asset DVD
Download materials from FSS
Request participation in a Corporate release
Request participation in an Essential release
Decide where to host Downloadable Word and PDF files
Request CMS Channel
Translate Variables for the CMS
Translate Variables for Moodle
Content
Localize and Translate My Work scripts (Surveys and assessments)
Localize and Translate Essentials Online Course scripts
Localize and Translate Facilitation Tab scripts
Localize and Translate Resource files
Localize and Translate DEP and AP Content
Create and submit an Adaptation Plan
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Optional: attend a Robohelp Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account
Schedule the Site Admin and Course Authoring orientation
Complete the online self study Create a Course Environment.
RTA Training
Web Production
Load the DEP and AP content in the CMS
Review and approve the DEP and AP content in the CMS
Post word and pdf files
Moodle Production
Build the Course
Post word and pdf files
Create Manage screen shots and other images
Create annimated demonstrations
Web Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 QA Build 002 QA Build 003 QA Build 004 QA Build 005 QA Build 006 QA Build 007 QA Build 008
Fix defects
Moodle Quality Assurance
Review the content and course functionality using a Test Script
Fix defects
Web Final Production
Launch
Moodle Final Production
Launch
CD Production
Review the CD to identify what files need to included NOTE: Materials have already been translated as part of the content scripts or resource documents. Help Guide goes on the CD as well as other identified documents
Produce a CD
Print CD for pilot
Pilot
Conduct a Pilot
Edit the Pilot Content
Integrate the Pilot Revisions
Conduct a Final Web Review
Final Production
Print Final CD Materials
Print Final Folder Materials
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21 | ww22 | ww23 | ww24 | ww25 | ww26 | ww27 | ww28
Planning
Schedule Project Orientation Meeting | WM | 1 Day | bar: ww1
Request team accounts to File Sharing site | WM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | WM | 1 Day | bar: ww1
Schedule Project Status meetings | WM | 1 Day | bar: ww1
Set Up
Obtain a copy of the Curriculum Guidelines Asset DVD | EM | 1 Day | bar: ww1
Download materials from FSS | RTA | 1 Day | bar: ww1
Request participation in a Corporate release | WM | 1 Day | bar: ww1
Request participation in an Essential release | WM | 1 Day | bar: ww1
Decide where to host Downloadable Word and PDF files | WM | 1 Day | bar: ww1
Request CMS Channel | WM | 1 Day | bar: ww1
Translate Variables for the CMS | RTA | 1 week | bar: ww2
Translate Variables for Moodle | RTA | 1 week | bar: ww2
Content
Localize and Translate My Work scripts (Surveys and assessments) | RTA | 1 week | bar: ww3
Localize and Translate Essentials Online Course scripts | RTA | 1 week | bar: ww4
Localize and Translate Facilitation Tab scripts | RTA | 1 week | bar: ww5
Localize and Translate Resource files | RTA | 2 weeks | bar: ww6 to ww7
Localize and Translate DEP and AP Content | RTA | 4 weeks | bar: ww8 to ww11
Create and submit an Adaptation Plan | EM | 1 Day | bar: ww11
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww4 to ww12
Edit the content | 2nd ST trainer | cycle | bar: ww5 to ww13
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww6 to ww14
Training
Optional: attend a Robohelp Training | PT and RTA | 1 Day | bar: ww8
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account | PT and RTA | 1 Day | bar: ww9
Schedule the Site Admin and Course Authoring orientation | PT and RTA | 1 Day | bar: ww7
Complete the online self study Create a Course Environment. | PT and RTA | 1 week | bar: ww7
RTA Trainign | RTA | 4 Days | bar: ww8 to ww9
Web Production
Load the DEP and AP content in the CMS | PT | 4 weeks | bar: ww12 to ww15
Review and approve the DEP and AP content in the CMS | PT | 1 week | bar: ww15
Post word and pdf files | PT | 1 week | bar: ww15
Moodle Production
Build the Course | PT | 5 weeks | bar: ww8 to ww12
Post word and pdf files | PT | 1 week | bar: ww12
Create Manage screen shots and other images | PT | 1 week | bar: ww12
Create annimated demonstrations | PT | 1 week | bar: ww13
Web Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 | PT | 1 Day | bar: ww11
QA build 002 | PT | 1 Day | bar: ww12
QA Build 003 | PT | 1 Day | bar: ww12
QA Build 004 | PT | 1 Day | bar: ww13
QA Build 005 | PT | 1 Day | bar: ww13
QA build 006 | PT | 1 Day | bar: ww14
QA Build 007 | PT | 1 Day | bar: ww14
QA Build 008 | PT | 1 Day | bar: ww15
Fix defects | PT | during Builds | bar: ww13 to ww15
Moodle Quality Assurance
Review the content and course functionality using a Test Script | PT | 1 week | bar: ww13
Fix defects | PT | 1 week | bar: ww14
Web Final Production
Launch | Corporate Team | 1 week | bar: ww16
Moodle Final Production
Launch | RTA | 1 week | bar: ww15
CD Production
Review the CD to identify what files need to included NOTE: Materials have already been translated as part of the content scripts or resource documents. Help Guide goes on the CD as well as other identified documents | RTA | 1 week | bar: ww13
Produce a CD | PT | 1 week | bar: ww14
Print CD for pilot | RTA | 1 week | bar: ww15
Pilot
Conduct a Pilot | EM | 6 weeks | bar: ww17 to ww22
Edit the Pilot Content | RTA | 1 week | bar: ww23
Integrate the Pilot Revisions | PT | 1 week | bar: ww24
Integrate Final Edits into the Design Templates | RTA | 2 weeks | bar: ww25 to ww26
Final Production
Print Final Materials | RTA | 1 week | bar: ww27
Print Final Folder Materials | RTA | 1 week | bar: ww27
Post Project
Reflect on the Project | EM or WM | 1 week | bar: ww28
Document BKMs | EM or WM | 1 week | bar: ww28
WM=Web Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Project Deadline Date>
Modules/Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date
<Enter Web Release Month>
Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date | CMS Entry | Date | Approver | Date