## Content Overview
Project Plan: | Essentials Online
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Request participation in an Essentials Online release
Decide where to host Downloadable Word and PDF files
Download materials from FSS Use the Set Up Procedure
Translate Moodle Variables File found under Technical Translations in the Essentials Online FSS
Content
Localize and Translate My Work scripts (Surveys and assessments)
Localize and Translate Essentials Online Course scripts
Localize and Translate Facilitation Tab scripts
Localize and Translate Resource files
Create and submit an Adaptation Plan
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Schedule the Site Admin and Course Authoring orientationdelivered by the Corporate Team.
Complete the online self study Create a Course Environment.
Web
Build the Course
Post word and pdf files
Create Manage screen shots and other images
Create annimated demonstrations
Quality Assurance
Review the content and course functionality using a Test Script
Fix defects
Conduct a Pilot
Final Production
Edit the Pilot Content
Integrate the Pilot Revisions
Conduct a Final Web Review
Review the CD to identify what files need to included NOTE: Materials have already been translated as part of the content scripts or resource documents. Help Guide goes on the CD as well as other identified documents
Produce Resource CD
Print folder and inserts
Launch
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21
Planning | bar: ww1 to ww16
Schedule Project Orientation Meeting | WM | 1 Day | bar: ww1
Request team accounts to File Sharing site | WM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | WM | 1 Day | bar: ww1
Schedule Project Status meetings | WM | 1 Day | bar: ww1
Set Up | bar: ww1 to ww16
Request participation in an Essentials Online release | WM | 1 Day | bar: ww1
Decide where to host Downloadable Word and PDF files | WM | 1 Day | bar: ww1
Download materials from FSS Use the Set Up Procedure | RTA | 1 Day | bar: ww1
Translate Moodle Variables File found under Technical Translations in the Essentials Online FSS | EM/RTA | 1 week | bar: ww2
Content | bar: ww1 to ww16
Localize and Translate My Work scripts (Surveys and assessments) | RTA | 1 week | bar: ww3
Localize and Translate Essentials Online Course scripts | RTA | 1 week | bar: ww4
Localize and Translate Facilitation Tab scripts | RTA | 1 week | bar: ww5
Localize and Translate Resource files | RTA | 2 weeks | bar: ww6 to ww7
Create and submit an Adaptation Plan | EM | 1 week | bar: ww8
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww4 to ww8
Edit the content | 2nd ST trainer | cycle | bar: ww5 to ww9
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww6 to ww10
Training
Schedule the Site Admin and Course Authoring orientation delivered by the Corporate Team. | PT and RTA | 1 Day | bar: ww7
Complete the online self study Create a Course Environment. | PT and RTA | 1 Day | bar: ww7
RTA Training | RTA | 4 days | bar: ww7 to ww8
Web
Build the Course | PT | 5 weeks | bar: ww7 to ww10
Post word and pdf files | PT | 1 week | bar: ww10
Create Manage screen shots and other images | PT | 1 week | bar: ww10
Create annimated demonstrations | PT | 1 week | bar: ww10
Quality Assurance
Review the content and course functionality using a Test Script | PT | 1 week | bar: ww11
Fix defects | PT | 1 week | bar: ww11
Conduct a Pilot | EM | 6 weeks | bar: ww12 to ww17
Final Production
Edit the Pilot Content | RTA | 1 week | bar: ww17
Integrate the Pilot Revisions | PT | 1 week | bar: ww18
Conduct a Final Web Review | RTA | 1 week | bar: ww19
Review the CD to identify what files need to included NOTE: Materials have already been translated as part of the content scripts or resource documents. Help Guide goes on the CD as well as other identified documents | RTA | 1 week | bar: ww18
Produce Resource CD | PT | 1 week | bar: ww20
Print folder and inserts | PT | 1 week | bar: ww20
Launch | Corporate Team | 1 week | bar: ww20
Post Project
Reflect on the Project | EM or WM | 1 week | bar: ww21
Document BKMs | EM or WM | 1 week | bar: ww21
WM=Web Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Web Release Month>
Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date | Moodle Entry | Date | Moodle Reviewer | Date