## Content Overview
Project Plan: | Thinking With Technology Course
Intel Project Owner: | <insert name>
RTA Project Leader: | <insert name>
Project Deadline: | <insert deadline; if multiple deliverables, add rows to note those>
Task | Owner | Due Date | Status | Comments
Planning
Schedule Project Orientation Meeting
Request team accounts to File Sharing site
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines
Schedule Project Status meetings
Set Up
Obtain a copy of the Curriculum Guidelines Asset DVD
Download materials from FSS
Request participation in a Corporate release
Decide where to host Downloadable Word and PDF files
Request CMS Channel
Translate Variables for the CMS and Workspace
Content
Localize and Translate Manual
Localize and Translate CMS Tools Content
Localize and Translate CD Materials
Create and submit an Adaptation Plan
Teacher Workspace launched
Create Teacher Workspace Examples
Review localized and translated content to ensure local educational meaning and terminology
Edit the content
Deliver the translated content to the production team
Training
Optional: attend a Quark or Robohelp Training
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account
Web Production
Load the content in the CMS
Review and approve the content in the CMS
Post word and pdf files
Web Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 QA Build 002 QA Build 003 QA Build 004 QA Build 005 QA Build 006 QA Build 007 QA Build 008
Fix defects
Web Final Production
Launch
Manual/CD Production
Produce the Manual
Produce a CD
Print Manuals and CD for pilot
Manual/CD Quality Assurance
Conduct a Pilot
Edit the Pilot Content
Integrate the Pilot Revisions
Integrate Final Edits into the Design Templates
Final Production
Print Final Materials
Post Project
Reflect on the Project
Document BKMs

## Timeline
Example Timeline
Task | Owner | duration | ww1 | ww2 | ww3 | ww4 | ww5 | ww6 | ww7 | ww8 | ww9 | ww10 | ww11 | ww12 | ww13 | ww14 | ww15 | ww16 | ww17 | ww18 | ww19 | ww20 | ww21 | ww22 | ww23 | ww24 | ww25 | ww26 | ww27 | ww28
Planning
Schedule Project Orientation Meeting | WM | 1 Day | bar: ww1
Request team accounts to File Sharing site | WM | 1 Day | bar: ww1
Schedule an overview of the Project File Sharing site for materials, expectations, and guidelines | WM | 1 Day | bar: ww1
Schedule Project Status meetings | WM | 1 Day | bar: ww1
Set Up
Obtain a copy of the Curriculum Guidelines Asset DVD | EM | 1 Day | bar: ww1
Download materials from FSS | RTA | 1 Day | bar: ww1
Request participation in a Corporate release | WM | 1 Day | bar: ww1
Decide where to host Downloadable Word and PDF files | WM | 1 Day | bar: ww1
Request CMS Channel | WM | 1 Day | bar: ww1
Translate Variables for the CMS and Workspace | RTA | 1 week | bar: ww2
Content
Localize and Translate Manual | RTA | 4 weeks | bar: ww3 to ww6
Localize and Translate CMS Tools Content | RTA | 4 weeks | bar: ww7 to ww10
Localize and Translate CD Materials | RTA | 2 weeks | bar: ww11 to ww12
Create and submit an Adaptation Plan | EM | 1 Day | bar: ww11
Teacher Workspace launched | Corporate Team | 2 weeks | bar: ww4 to ww5
Create Teacher Workspace Examples | Teacher | 2 weeks | bar: ww6 to ww7
Review localized and translated content to ensure local educational meaning and terminology | ST Trainer | cycle | bar: ww4 to ww13
Edit the content | 2nd ST trainer | cycle | bar: ww5 to ww14
Deliver the translated content to the production team | RTA | cycle, as files are done, they are delivered | bar: ww6 to ww15
Training
Optional: attend a Quark or Robohelp Training | PT and RTA | 1 Day | bar: ww6
Request a CMS Training Identify Author Identify Approver Provide IDSID Author and Approver must have an Intel account | PT and RTA | 1 Day | bar: ww10
Web Production
Load the content in the CMS | PT | 4 weeks | bar: ww10 to ww13
Review and approve the content in the CMS | PT | 1 week | bar: ww13
Post word and pdf files | PT | 1 week | bar: ww13
Web Quality Assurance
Submit content in scheduled QA cycles called builds QA Build 001 | PT | 1 Day | bar: ww11
QA build 002 | PT | 1 Day | bar: ww12
QA Build 003 | PT | 1 Day | bar: ww12
QA Build 004 | PT | 1 Day | bar: ww13
QA Build 005 | PT | 1 Day | bar: ww13
QA build 006 | PT | 1 Day | bar: ww14
QA Build 007 | PT | 1 Day | bar: ww14
QA Build 008 | PT | 1 Day | bar: ww15
Fix defects | PT | during Builds | bar: ww13 to ww15
Web Final Production
Launch | Corporate Team | 1 week | bar: ww16
Manual/CD Production
Produce the Manual | PT | 5 weeks | bar: ww4 to ww8
Produce a CD | PT | 1 week | bar: ww13
Print Manuals and CD for pilot | RTA | 1 week | bar: ww14
Manual/CD Quality Assurance
Conduct a Pilot | EM | 6 weeks | bar: ww17 to ww22
Edit the Pilot Content | RTA | 1 week | bar: ww23
Integrate the Pilot Revisions | PT | 1 week | bar: ww24
Integrate Final Edits into the Design Templates | RTA | 2 weeks | bar: ww25 to ww26
Final Production
Print Final Materials | RTA | 1 week | bar: ww27
Post Project | bar: ww1 to ww21; ww28
Reflect on the Project | EM or WM | 1 week | bar: ww28
Document BKMs | EM or WM | 1 week
WM=Web Manager
EM=Education Manager
PT=Production Team

## Project Roadmap
Project Roadmap: <Insert Project Name>
<Enter Project Deadline Date>
Modules/Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date
<Enter Web Release Month>
Files | Translator | Date | Reviewer | Date | Editor | Date | Pilot/Adaptation Revisions | Date | Final Editor Approval | Date | CMS Entry | Date | Approver | Date