## Launch
Date | 2003-10-08 | Wed
Location | BofA registration, WFR event
Time Beg | 5:00
Time End | 0:00
Purpose: | to kick off business plan competition, increase awareness
Agenda 1pm-6:00pm
5:00 | 6;00 | Registration and Cocktail in BofA
6;00 | 6:10 | Intro, brief description of BPC
6:10 | 6:25 | Keynote Speaker
6:25 | 6:40 | Rules
6:40 | 6:45 | Key Dates
6:45 | 7:00 | Q&A
7:00 | 7:10 | Closing Remarks
Bank of America & Wells Fargo Room
Attire - blue bplan shirt
Registration |  | BofA (capacity x)
Registration desk
Computers for registration,
Launch |  | WFR (capacity X)
Chair setup with CED
AV -
To-do List |  |  | Due Date | Status
ReserveRoom
Finalize AV needs
Arrange AV
Arrange keynote speaker
Create slides
Finalize agenda
Send Kathryn parking needs (speaker)
Obtain parking needs (judges and mentors)
Finalize volunteering needs (registration table, photo)
Solicit volunteers
Finalize catering needs
Obtain linen for the registration table
Finalize marketing/PR needs
Finalize key dates
Create Key Fact Sheets
Send Kathryn organizer/Lester Ctr name for name tag
Make name tags
Finalize judging guidelines
| Setup rooms, registration desk |  | 2003-10-08
| Prepare registration sheet (name and email) |  | 2003-10-07
Catering Needs (refreshments)
Volunteers
Registration | 4
AV | 1
Photographer | 2 | - Take photos
Organizers/Lester Center Staff |  |  | Total

## Final Judging
Date | 2003-04-22 | TUE | # of Finalist | 30 | 6 teams max
Location | Judging Room (reserved 8:00am - 6:00pm) CONTACT:
Time Beg | 1:00
Time End | 6:00
Agenda 1pm-6:00pm
12:45 | 1:00 | Registration
1:00 | 1:10 | Welcome -> Thanks sponsors
1:10 | 1:30 | Judging Rule (15 min Prez, 10 min Q&A and 8 Del 2 min buffer = 35)
1:30 | 2:05 | Presentation #1
2:05 | 2:40 | Presentation #2
2:40 | 3:25 | Presentation #3
3:25 | 3:35 | Break |  |  |  | Set up Rm 124
3:35 | 4:10 | Presentation #4
4:10 | 4:45 | Presentation #5
4:45 | 5:20 | Presentation #6
5:20 | 5:30 | Break |  | - move to rm 124
5:30 | 6:00 | Deliberation (30min)
5 deliberation
Judging Room |  | Contact: Veronica
CAPACITY 367
* Deliberation to be held in rm 124 (capacity: 18, reservation 4-6)
* no food in room, lobby you can have food; catering on your own; tables there; alchohol permit by campus police
(contact Kathryn)
AV needs
AV - | media service
To-do List | [5 empty] | Due Date | Status
| Extend hours for Judging room |  |  |  |  | ASAP | x
| Finalize AV needs (2 Computer projector, overhead projector) Computer situation at Boalt Hall -- preload prez on 2 computers. |  |  |  |  | ASAP | x
| Arrange AV |  |  |  |  | ASAP | x
| Collect presentations |  |  |  |  | 2003-04-20 | x
| Preload Presentations on 2 computers |  |  |  |  | 2003-04-21
| Finalize agenda |  |  |  |  | ASAP | x
| Send Kathryn parking needs (judges) |  |  |  |  | ASAP | x
| Send Kathryn parking needs (mentors) and arrange parking w/ MBA office |  |  |  |  | ASAP | x
| Obtain parking needs (judges and mentors) | [5 empty] | x
| Obtain 8+6 =14 parking passes for Award Ceremony |  |  |  |  | 2003-04-21
| Finalize volunteering needs (facilitator, scribe (2), escort (1), greeters (2), registration (2)) |  |  |  |  | ASAP | x
| Confirm volunteer needs |  |  |  |  | ASAP | x
| Solicit volunteers |  |  |  |  | ASAP | x
| Arrange for facilitator |  |  |  |  | ASAP | x
| Finalize catering needs |  |  |  |  | ASAP | x
| Purchase food |  |  |  |  | 2003-04-20 | x
| Linen for the registration table? |  |  |  | JB | ASAP
| Contact campus police for alchohol license -> Faye |  |  |  |  | ASAP
| Finalize judges (8 judges) |  |  |  |  | 2003-03-21 | x
| Submit final judges to Andrea |  |  |  |  | 2003-03-21 | x
| judges name for name tag |  |  |  |  | 2003-04-18 | x
| mentor name for name tag |  |  |  |  | 2003-04-18 | x
| team name for name tag |  |  |  |  | 2003-04-18 | x
| organizer/Lester Ctr name for name tag |  |  |  |  | 2003-04-18 | x
| Make name tags |  |  |  |  | 2003-04-22
| Send invitations to judges |  |  |  |  | 2003-04-01 | x
| Submit finalist teams to Andrea |  |  |  |  | 2003-04-04 | x
| Send invitations to teams |  |  |  |  | ASAP | x
| Finalize judging guidelines |  |  |  |  | na | x
| Develop judging materials |  |  |  |  | na | x
| Send judging materials to judges and volunteers |  |  |  |  | 2003-04-15 | x
| Buy 8 folders, pen and whiteboard |  |  |  |  | 2003-04-21 | x
| Create note taking template |  |  |  |  | ASAP | x
| Distribute note taking template |  |  |  |  | 2003-04-21 | x
| Copy Biz Plans for judges |  |  |  |  | 2003-04-21 | x
| Make signs and time left card |  |  |  |  | 2003-04-21 | x
| Setup rooms, registration desk |  |  |  |  | 2003-04-22
| Attire - white shirt | [5 empty] | x
| Team Registration List |  |  |  |  | ASAP | x
| Mentor Registration List |  |  |  |  | ASAP | x
| Judges Registration List |  |  |  |  | ASAP
Things to Bring to Judging Room
Drinks, food
Facilitator's minutes left card
Signage
Agenda
Dry and Erase pen
Table Cloth
Mentors/judgesparking passes
Banner
Name tag
| Judges Package |  | notepads
Catering Needs (refreshments)
Volunteers
Faclitator | 2 | - Faciliatate Dicussion - Official time keeper
Scribe | 2 | - Take notes on computer - Read notes back to judges to facilitate judging - Take notes for team feedback - Backup: Andrea
Escort | 1 | - Ensure teams are in&out of rm on time - Any room needs are met
Registration | 2 | - Check in & out - Info Center - Check in judges and mentors - ask them if they are attending Award Ceremony. If so give parking.
Greeter | 2 | - Greet judges and lead them to Judging Room
AV | 1 | - Manage projector
Photographer | 2 | - Take photos
Video | 1
Organizers/Entrepreneurship Staff | [5 empty] | Total | 30

## Final Dinner
Date | 2003-04-22 | Tuesday
Location | Faculty Club (Great Hall): Capacity 120 | [5 empty] | confirmed
Prep Time
Time Beg | 18:30
Time End | 21:00
Agenda
18:30 | 19:30 | Cocktail
19:30 | 19:40 | Intro (10) |  | Special thank you to sponsors and judges
19:40 | 19:55 | Welcome (5m) |  |  | * confirm speech
19:55 | 20:50 | Dinner
20:50 | 21:00 | Closing remarks |  |  | Gift Giving????
To-do List | [5 empty] | Due Date | Status
| Reserve room |  |  |  |  | ASAP | x
| Finalize agenda |  |  |  |  | ASAP | x
| Finalize invitation list (Currently 216 people invited!!!) |  |  |  |  | ASAP | x
| Send out invitations (include RSVP cards * attendance, menu selection, RSVP to Matilde) |  |  |  |  | 2003-04-04 | x
| Collect RSVP |  |  |  |  | 2003-04-18 | x
| Confrim Jerry is speaking |  |  |  |  | ASAP
| Confrim Dean to speak -cannot attend |  |  |  |  | na | x
| Finalize AV needs (no music) |  |  |  |  | ASAP | x
| Arrange AV needs |  |  |  |  | ASAP
| Finalize parking needs - only judges and mentors get parking |  |  |  |  | ASAP | na
| Finalize dinner menu (see below) |  |  |  |  | ASAP | x
| Place initial order w/ Faculty Club |  |  |  |  | ASAP | x
| Give final catering numbers to Faculty Club |  |  |  |  | 2003-04-16
| Create Chicken or Veggie Ticket (to be handed out at Registration) |  |  |  |  | 2003-04-20
| Identify who to get gifts - all (8 judges + 6 final team mentors) will get a gift basket |  |  |  |  | ASAP | x
| Purchase gifts for judges |  |  |  |  | ASAP | x
| Determine when to give gifts |  |  |  |  | ASAP
| Identify volunteer needs |  |  |  |  | ASAP | x
| Solicit Volunteers |  |  |  |  | ASAP | x
| RSVP list for name tags |  |  |  |  | ASAP | x
| Create name tags |  |  |  |  | 2003-04-22
Budget Review
Catering Needs | [5 empty] | Budget | XX
ENTRES* |  |  |  | Est # of people
Podium, mike? |  | 50 | reserved
Invitation List (Andrea) | [5 empty] | Lead | Status
15 | Sponsors |  |  |  |  | Matt W.
20 | Mentors (4/4) |  |  |  |  | Matt G.
20 | Judges |  |  |  |  | Leo/Andre
45 | Team (only finalist teams) (4/4) |  |  |  |  | Matt G.
16 | BPC alums (co-chairs from '99-'02 (6), last years exec cmte (10)) |  |  |  |  | Dan
40 | 02 BPC Organizers |  |  |  |  | Dan
"24" | Lester Center VIP (advisory member) |  |  |  |  | Kathryn | x
1 | Dean |  |  |  |  | Matilde | x
| UCSF Staff |  |  |  |  | Dan
| SIMS deans |  |  |  |  | Dan
| Vertex Leadership |  |  |  |  | Dan
2 | Award Ceremony Speakers |  |  |  |  | Ilya
FYI: Previous Year Invite List Current and Past Organizers Current Teams (FINALIST teams only - we had 6 teams) Any sponsors you think relevant - including potential sponsors Finalist Team Mentors Final Round Judges Important people from Haas and UC Berkeley (inlcuding Lester Center staff like Sharon, Stephanie, Kathryn)
NOTE: No invitation to Russ Siegelman. (contact Matt Weathers)
Volunteers |  | Who
Registration Desk (3) |  |  | - Check in guests
6:00-6:45 |  |  | - Distribute meal tix
- Info Desk
- Direct VIPs to assigned tables
Greeters (4) |  |  | - Greet people @ Cronk Gate
5:50-6:45
Photographer (2) |  |  | - Bring digital Camera

## Award Ceremony
Date | 2003-04-23 | Wednesday
Location | Andersen Auditorium (Reception BofA)
Prep Time
Time Beg | 18:00
Time End | 21:00
Agenda | * MC - Ilya & Dan
18:00 | 18:30 | Reception
18:40 | 18:45 | Opening (5)
18:45 | 18:50 | Jerry (5)
18:50 | 19:05 | Keynote Speech (Nick Sturiale, Sevin Rosen Funds) - 10 min
19:05 | 19:10 | People's Award Rules (3 min prep, 7min PreZ and 3min Q&A)
19:10 | 20:28 | Team Presentations (13 min/ team 6 teams = 78 min) Order same as final judging.
20:28 | 20:43 | Speech (Scott K., zipRealty) - 15 min * Tally people's awards votes (33 min)
20:43 | 20:55 | Slide show (10) ** ANY OTHER IDEAS? **
20:55 | 21:15 | Present Awards (30)
21:15 | 21:20 | Closing Remarks
To-do List | [5 empty] | Due Date | Status
Kathryn | Confirm room reservations |  |  |  |  | ASAP | x
Ilya | Arrange speaker - Scott, Jerry and Nick |  |  |  |  | ASAP | x
Matilde | Finalize agenda |  |  |  |  | ASAP | x
Matilde | Develop people's award logistics 1) as people enter the room, give them ballots (people select choice 1 and 2) 2) after the prez, have 4 people run up and down the aisles with a box to collect ballots 3) bring all the boxes to side room 4) Counters put the ballots into the box with the team names (if winning team gets the choice 1, the choice 2 gets the vote) 5) Counters count the number of ballots per team. 6) Notify xxx for check writing and announcement | [5 empty] | x
Leo/Andre | Finalize People's Choice Rules
Leo/Andre | Create People's Choice Ballots
Matilde | Create box for each team, and ballot collection box |  |  |  |  | 2003-04-20
Arturo/Brad | Finalize AV needs (Music? Cordless mike?, Projector - Rotating Slide Show) |  |  |  |  | ASAP
Arturo | Arrange AV needs |  |  |  |  | ASAP
Yvonne | Collect favorite songs and prez from teams | [5 empty] | x
Arturo | Assemble slides |  |  |  |  | 2003-04-23
Andrea | Determine INVITE list |  |  |  |  | ASAP | x
Andrea | Send out invitations |  |  |  |  | ASAP | x
Kathryn | Obtain 16 parking permits (Keynote speakers (2), Final Judges (8) and mentors (6)) |  |  |  |  | 2003-04-15
Matilde | Check to see if we need secuirty - no | [5 empty] | x
AM/DH/BH | Develop the rotating slide show (sponsorship recognition) |  |  |  |  | 2003-04-22 | x
Ilya | Distribute parking passes to speakers *no greeters at Cronk Gate
All | Identify volunteer needs - Facilitator - Timekeeper - Arturo - Ballot counter (12) - Ballot handler (4) - Q&A runner - getting the mikes to the people (2) - Photographer (1) |  |  |  |  | ASAP | x
Matilde | Arrange volunteers |  |  |  |  | 2003-04-15 | x
Matilde | Create Final Day Package (agenda, roles etc) |  |  |  |  | 2003-04-17 | x
MK/AM | Communicate to volunteers roles and responsibility |  |  |  |  | 2003-04-17
Arturo | Create Photo Slideshow to be shown during dead hour |  |  |  |  | 2003-04-20
Brad | Create the check |  |  |  |  | ASAP | x
All | Check writing process?? Who signs the check? -> Brad and Kathryn | [5 empty] | x
Matilde | Finalize catering needs for the reception - JB |  |  |  |  | ASAP | x
Kathryn | Reserve location - BofA: share w/ IBD |  |  |  |  | ASAP | x
Matilde | IBD contact person - Erin - to coordinate catering |  |  |  |  | ASAP | x
Dan | People's Award rule -- ask Jerry can 1st fet PCA?
Arturo | Vedio Camera? | [5 empty] | x
Real Camera?
Leo/Andre | Attire - Blue t-shirt - Leo to provide Heather N., Yvonne L. and Ross M. t-shirts
Setup Needs
Mini-pencils
Envelop
Set aside seats for teams
Volunteers
MC | Dan
Ilya
Facilitator | Dan/Ilya | - Facilitate Team Prez and Q&A
Time keeper | Leo D. | - Time Keeper
Scribe | Scott B. | - Record Questions during Q&A
Ballot counter |  | - Hand out ballots and programs when people enter the room
| Yvonne L. | - Collect ballots at the end of the Prez
| Lindsay D. | - Count ballots (2 people per team)
| Ross M. | - Report results to Brad
Dave H.
Andrea K.
Tom C.
Q&A Runner | Andrea K. | - Give mikes to people
Greeter | Scott B. | 5:45-6:20
| Leo D. | Greet people at the Cronk Gate
Brad H.
Matt G.
Andre M.
Photographer | Taylor
Arturo
Video Camera | Arturo
Catering
Jimmy Beans
$1500 total
|  |  | # | Price | Extension
|  | Reg/Decaf Coffee w/setup | 30 | 1.5 | 45
|  | Asst. Soft Drinks | 300 | 1.5 | 450
|  | Asst. cookies & brownies | 200 | 1 | 200
|  | Appetizer menu #1 | 100 | 6.5 | 650
Assorted finger sandwiches
Assorted aram sandwiches
Crudite platter with dips
|  | Tablecloth | 3 | 5.5 | 16.5
|  |  |  | subtotal | 1361.5
|  |  |  | 8.25% tax | 112.3238
|  |  |  | total | 1473.8238
Clean - up?

## Mentor Mixer
Mentoring Mixer
Purpose | Teams meeting the Mentors for the first time.
Contact: | Matt, Yvonne
Date | 2003-02-13 | THUR | # of Semi-finalist | 75
Location | Wells Fargo Room |  | # of Metors | 25
Prep | 18:30 |  | Others | 4 | Jerry, Sharon, Eric, Kathryn
Time Beg | 19:00 |  | Volunteers | 9 | Yvonne, Matt, Vikaash, Albert, Annie, Dan, Ilya, Arturo, Matilde
Time End | 21:00 |  | Total # of people | 113
Parking | mentors only |  | 80% attendance | 90.4
Table/chair | 7 tables
Agenda
18:30 | 19:00 | Prep (put up signs, reg table setup, room setup)
19:00 | 19:30 | Registration, Gift giving, Mingling
19:30 | 19:35 | Jerry speaks and introduces Matt and Yvonne |  |  |  |  | confirmed
19:35 | 19:45 | Matt and Yvonne speak and introduces keynote speaker
19:45 | 20:00 | Keynote speaker
20:00 | 20:50 | Mingle
20:50 | 21:00 | Matt to announce end of the event and thank people for coming
To-do List | [5 empty] | Due Date | Status
Tom | Update Website Material |  |  |  |  | ASAP | x
Matt | Reserve parking (via Kathryn) |  |  |  |  | 2003-01-07 | x
Matt/Mkting | Send out invitation to mentors (incl parking instructions) |  |  |  |  | 2003-02-03
MK/AM | Double check room reservation (Wells Fargo Rm) |  |  |  |  | 2003-01-22 | x
AM | Reserve mike and podium, in-focus projector |  |  |  |  | 2003-01-31 | x
Matt | Arrange keynote speaker (Erik Hom of CherryTree Securities), run it by Jerry |  |  |  |  | 2003-01-24 | x
Sharon | Confirm Jerry to speak |  |  |  |  | 2003-01-24 | x
MK/Sharon | Catering (cocktail party style), beer & wine, appetizer, linen, center pieces |  |  |  |  | 2003-01-24 | x
Matt | Look into doing a slideshow of previous years' photo (AV) |  |  |  |  | 2003-01-31
Sharon | Look for previsous year's album (matt) |  |  |  |  | 2003-02-01 | x
YL | Purchase stickers for team-mentor matching |  |  |  |  | 2003-02-03
Marketing | Create signs to Wellsfargo Brad will bring the banner to the mixer |  |  |  |  | 2003-02-13
YL | Create Launch album |  |  |  |  | 2003-02-03
Matt/YL | Submit final RSVP list (mentor and semi-finalists to Kathryn for name tag) |  |  |  |  | 2003-02-11
Matt | Submit # of attendee to Sharon for catering (final no by 2/11) |  |  |  |  | 2003-02-07
AM | Solicit digital camera |  |  |  |  | 2003-02-07 | x
Matt/YL | Prepare gifts for mentors |  |  |  |  | 2003-02-07
Matt/Mkting | Send out invitation to semi-finalists |  |  |  |  | 2003-02-12
Matt/Mkting | Produce info packages to be handed out (critical dates etc) Use the Launch Material (Matilde to bring to room) |  |  |  |  | 2003-02-12 | x
Matt/Kathryn | Prepare Registration Material |  |  |  |  | 2003-02-13
Kathryn | Create name tags (Katherine to print) |  |  |  |  | 2003-02-12
$$$$$$$$] |  |  | Budget | Actual
Space |  |  | 175
Catering |  |  | 2124.95
Stickers
Parking ($15 ea) |  |  | 450
Gifts
Signs
AV (mike) |  |  |  | 0
Total |  |  | 2749.95 | 0
The Day Of
Banner |  |  | Brad
Promotion Material |  |  | Matilde
Digital Camera |  |  | Arturo
AV (mike & projector) |  |  | AV
Registration Material |  |  | Matt/Kathryn
Name tag |  |  | Kathryn
Gifts for the mentors |  |  | Matt/Yvonne
Catering
Catering Co. | Santa Fe
Wine
Beer
Softdrinks
Appetizer
Linen
Ceter Piece
Silverware
Notes
A. | No music
B. | Tables around the room
C. | Reg table manning (YL, Matt, XXX, XXX, XXX)