Chapter 1

This part of the Windows 95 Resource Kit provides a comprehensive guide to installing and deploying Microsoft Windows 95 for network administrators and support professionals in large organizations. This guide was created by talking 
with administrators of corporate networks about their testing and rollout plans for Windows 95.

Deployment Guide for Windows 95: Overview

The Deployment Guide is organized into two chapters:

·	The first chapter provides a quick run-through of the significant steps in the deployment schedule.

·	The next chapter, “Planning the Details,” explains in more depth the key decisions or actions listed in the overview.

For step-by-step instructions for conducting the installation, you’ll want to read Chapter 3, “Introduction to Windows 95 Setup,” and Chapter 4, “Network Setup,” in the Windows 95 Resource Kit.

Overview of the Process    1-2

@In This Chapter

I.      Review the Product    1-2

II.     Assemble the Evaluation Team and Tools    1-4

III.    Specify the Preferred Client Configurations    1-5

IV.    Lab-Test the First Installation    1-9

V.     Evaluate and Plan the Installation Process    1-12

VI.    Pilot-Test the Installation    1-15

VII.  Create the Rollout Plan    1-16

VIII. Conduct the Installation    1-18

# Overview of the Process

The deployment process for Windows 95 is divided into distinct phases that span everything from how to evaluate Windows 95, to how to automatically install Windows 95 without actually visiting the client computers. The deployment phases are the following:

I.		Review the Product

II.		Assemble the Evaluation Team and Tools

III.		Specify the Preferred Client Configuration

IV.		Lab-Test the Installation

V.		Evaluate and Plan the Installation

VI.		Pilot-Test the Installation

VII.	Create the Rollout Plan

VIII.	Deploy Windows 95

In the summaries presented for each phase in this chapter, we provide checklists that describe the tasks for the specific phase. The following briefly shows how you can use these checklists at your site.

Checklist Example

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Summary description of the task. Details are provided in Chapter 2, “Planning the Details.” | Who will work on this task? | When does this task start? | Length of task? |

# I.	Review the Product

Windows 95 offers an extremely broad and powerful feature set that dramatically impacts the cost and structure of your organizational computing infrastructure. Understanding how the Windows 95 feature set can help you reduce your support costs and increase your systems control is important to implementing it correctly and most efficiently. For example, in Windows 95 one new feature – system policies – enables you to remotely administer and manage user capabilities on client computers. Closely examining the new and enhanced features in Windows 95 is the first step in planning the rollout process.

Windows 95 is also designed to make deployment easier and more powerful. By understanding how best to plan and automate the installation process, you can potentially reduce the cost of migration threefold, such that it costs significantly less than the migration from Windows 3.0 to Windows 3.1. For information about ownership costs, migration costs, and productivity benefits, you’ll want to read the Gartner Group’s research notes on Windows 95 and forthcoming information from Microsoft on business justifications for Windows 95.

In addition, you may want to read detailed publications such as the Windows 95 Reviewe’s Guide or the Inside Windows 95 book for in-depth information on Windows 95 and how it works.

Review Windows 95 Features

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Read the Windows 95 Reviewer’s Guide available on Microsoft WIN_NEWS forums which are located on popular BBS and Internet locations. See Chapter 2, “Planning the Details” or Appendix G, “Windows 95 Resource Directory,” the Resource Directory for exact locations. |  |  |  |
| 2: Review Total Cost of Ownership, Migration, and Productivity studies conducted by analysts such as Gartner Group to assess the impact of Windows 95 on your business’s bottom line. |  |  |  |
| 3: Optionally, attend one of the Microsoft IS Professionals Seminar and Tour sessions. |  |  |  |
| 4: Optionally, for technical details on the inner workings of Windows 95, read Inside Windows 95 from Microsoft Press book. |  |  |  |

# II.		Assemble the Evaluation Team and Tools

After you’ve read about the Windows 95 feature set and understood how it can reduce your on going support costs and lessen your migration costs through automated installation, you’ll want to assemble the people and tools for deployment. At this early phase of the process you need only a few resources to help you plan the broader installation that comes after extensive testing. The tasks for assembling the resources are described in the following list.

Assemble the Evaluation Team and Tools

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Assign the project manager. |  |  |  |
| 2: Select key planning and implementation team members. |  |  |  |
| 3: Acquire Windows 95, and the Windows 95 Resource Kit and Reviewer’s Guide. |  |  |  |
| 4: Profile and inventory your client and server hardware and software configurations on the network. |  |  |  |
| 5: Secure a testing lab. |  |  |  |
| 6: Acquire test computers for clients and servers. |  |  |  |
| 7: Install the application software and line-of-business tools in the lab to simulate the network environment. |  |  |  |
| 8: Have the implementation team review features in the Windows 95 Resource Kit Guided Tour and the Reviewer’s Guide. Study the Installation chapters in the Resource Kit. |  |  |  |
| 9: If needed, send team members to a Microsoft Authorized Technical Education Center for additional training. |  |  |  |

# III.		Specify the Preferred Client Configurations

With the evaluation team assembled and educated about Windows 95 capabilities, it is time to specify the preferred client configurations for testing. This is a paper exercise in which you choose the layout, configuration, and feature set to implement for each of your preferred client setups. For the purposes of discussion, “client computer” refers to any computer running Windows 95, including computers that run peer sharing services.

For any given feature or capability, such as the network redirector or a particular protocol implementation, there are several options and implementations to choose from. You will choose the appropriate implementation, based on its compatibility, performance, and functionality. Although you can arrive at the preferred client configuration from a number of angles, based on the degree of feature testing you require, we recommend that you work back from an ideal client to one that fits your company’s needs. This tends to be the simplest approach, but still lends itself to rigorous lab-testing if you require extensive side-by-side evaluation.

The recommended approach outlines a generic, ideal client configuration. Each of the features is then reviewed, considering its alternatives, including whether it is required at all. Not all decisions will be clear-cut in this specification phase and thus require testing of alternatives in the lab.

The following table lists the key features and capabilities of the ideal client and the related alternatives. Work through this table, checking off the features you plan to implement. You might not immediately recognize all the features or capabilities described in the list. You can read about these features in Chapter 2, “Planning the Details,” or in the related Resource Kit chapters listed in the table.

To be provided:  Preferred Client Configurations for the following:  Client on a Netware Network, Client on a Windows NT Server Network, Client on Other Networks. The following are some general recommendations.

Layout Decisions

| Configuration option | Decisions and issues | Related chapter |
| --- | --- | --- |
| Location of Windows files To maximize performance, security, or hard disk space on the client computer | Depends on your need to maximize ease of central security and administration versus performance on the client comptuer. Also affected by the hardware platform of the client machine. Options: · Run Windows on the client compture for best performance · Run Windows from the server for easier security and management · Run completely from the server as in diskless workstations | Chapter 4, “Network Setup” |

Key Features of the Ideal Network Client

| Preferred feature | Decisions and issues | Related chapter |
| --- | --- | --- |
| Use 32-bit, protected-mode network client software To provide the best network performance and functionality under Windows | Depends on the compatibility of your required applications and TSRs. Options, depending on the network. For example, for Novell® NetWare® networks: · Portected-mode Client for NetWare Networks is the preferred client. · Real-mode Novell NETX or VLM client is compatible with Windows 95. · A real-mode network client for another network can also be used if you use Client for NetWare Networks. | Page XX in Chapter 2, “Planning the Details” Chapter 8, “Windows 95 on Microsoft Networks” and Chapter 9, “Windows 95 on NetWare Networks” |
| Use 32-bit, protected-mode protocol To provide the best network performance and functionality under Windows 95 | Depends on the compatibility with your network. Options, depending on your choice of protocol. For example, for IPX/SPX: · Microsoft IPX/SPX-compatible protocol is preferred (with or without IPX over NetBIOS). · Real-mode IPX/SPX is the second choice. · Both the real-mode and Microsoft protected-mode implementation can be used. | Page XX in Chapter 2, “Planning the Details” Chapter 7, “Network Technical Issues” |
| Use the latest network adapter card drivers To provide the ability to load and unload the network and notify the rest of the system, use NDIS 3.1 drivers, which support Plug and Play | Depends on availability and compatibility of a new driver. Choose the older driver if a new driver is unavailable or if problems arise with the newer driver. Options: · The newest drivers are implemented by default. · You can manually choose an older driver, including ODI drivers. | Page XX in Chapter 2, “Planning the Details” Chapter 7, “Network Technical Issues” |
| Use long filenames. To provide greater ease of use in naming files and directories | Depends on whether you want to support long filenames in a mixed operating system environment, among users who share files. Options: · Long-filename capability is installed by default. · You can manually choose not to use long filenames during Windows 95 Setup. | Page XX in Chapter 2, “Planning the Details” Chapter 15, “Disks and File Systems” |

The following features in Windows 95 can also be selected for your preferred configuration. These features define how Windows 95 will be installed and administered at your site. We strongly recommend that you take advantage of these features at your site.

Recommended Windows 95 Features for Client Configurations

| Windows 95 feature | Decisions and issues | Related chapter |
| --- | --- | --- |
| Use system policies To pre-configure desktop security, and access to controls and features | Using system policies is an obvious choice if you need to control client access and security. No good substitutes are currently available. · Use System Policy Editor to define policies. · Use Network Setup, instead, to configure the same kinds of parameters – you won’t have central control. | Page XX in Chapter 2, “Planning the Details” Chapter 12, “System Management” |
| Use user profiles To allow multiple users to use a single PC with their own settings or conversely, one user on multiple to allowcomputers | Pre-configured desktop settings cause a slightly longer logon process while the configuration is loading. This delay is negligible, and no substitutes for User Profiles are available. Options: · The administrator can control whether the user can change options defined in the profile. · User profiles can be predefined to be used as part of Windows 95 installation. | Page XX in Chapter 2, “Planning the Details” Chapter 12, “System Management” |
| Enable remote administration To allow an admininistrator to remotely manage the file system, network sharing, or Registry of the local system | No substitutes for this feature are available. Options: · You must to specify installation of remote administration capabilities during Windows 95 Setup. This can be defined in a batch script. · No action is required if the feature is not needed. | Page XX in Chapter 2, “Planning the Details” Chapter 12, “System Management” |
| Use batch scripts for installation To allow an automated installation of the client | You’ll definitely want to use this feature if you must install Windows 95 on more than five computers. Options: · You must manually create a batch script once the client configuration is identified. · No action is required if the feature is not needed. | Page XX in Chapter 2, “Planning the Details” Chapter 4, “Network Setup” |
| Set up for push installation To allow the administration to push the installation out from the server without touching the client computer | You will want to use push installation if you must install Windows 95 on more than 50 computers. Options: · Edit the logon script. · Use a tool such as the Microsoft System Management Server | Page XX in Chapter 2, “Planning the Details” Chapter 4, “Network Setup” |

Recommended Windows 95 Features for Client Configurations, continued

| Windows 95 feature | Decisions and issues | Related chapter |
| --- | --- | --- |
| Use peer resource sharing services To allow each client to share files and resources such as printers and CD-ROM drives with other computers | Depends on your site’s security needs. If you are comfortable with users sharing local resources on their computers, then peer sharing can save network traffic and hard disk space on the server. Options: · You can only install this service on computers that use a 32-bit, protected-mode network client. · You must manually choose this during installation. · No action is required if the feature is not needed. | Page XX in Chapter 2, “Planning the Details” Chapter 8, “Windows 95 on Microsoft Networks,” and Chapter 9, “Windows 95 on NetWare Networks” |
| Use security To implement the user-level security from your network server for the peer sharing services | The decision depends on whether your site uses NetWare servers or servers running the Windows NT Server server operating system servers with central user accounts to provide security validation. Options: · User-level is preferred (and required in the case of File and Printer Sharing for NetWare) if it is available. · Share-level is easier, but less secure. | Page XX in Chapter 2, “Planning the Details” Chapter 11, “Security” |

Other Optional Windows 95 Features

| Windows 95 feature | Decisions and issues | Related chapter |
| --- | --- | --- |
| Use the Microsoft Exchange Mail capability To have a unified Inbox for messages, faxes, and so on | Depends on whether you have an existing mail system and whether you need Microsoft Exchange capabilities such as At Work Fax. Options: · Implement all or parts of Microsoft Exchange manually during the installation. · Use an existing mail package. · No action is required if the feature is not needed. | Page XX in Chapter 2, “Planning the Details” Chapter 19, “Microsoft Exchange and Mail” |
| Use value-added features To enable other Windows 95 ease-of-use innovations and capabilities [To be provided: Detail on additional features such as Remote Dial-in, At Work Faxing, and so on] | Depends on preference and need. In general, if you have the hard disk space and don’t use a third-party utility or application with the same capabilities, you should install the new features. Options: · Manually choose during Custom Setup or by selecting Typical, Laptop, or Minimal. · No action is required for typical feature installation, assuming sufficient hard disk space. | Page XX in Chapter 2, “Planning the Details” Chapter 3, “Introduction to Windows 95 Setup” |

# IV.	Lab-Test the First Installation

Now that you have specified the preferred client configurations on paper, it is time to lab-test them to see if they meet your compatibility, performance, and functionality needs.

Installing the software is a two-part process. In general, you’ll want to conduct an automated installation from a central server when installing Windows 95 at your site. This requires most of the upfront work to go into setting up the server correctly with the appropriate system and configuration files. This information is covered in the next phase. The client installation is then relatively easy.

For the sake of lab-testing the preferred client configuration, we recommend that you install directly from the Windows 95 compact disc. This simplifies the number of steps to begin learning and testing, and allows you to focus on getting the preferred client to work correctly.

Success in this phase is measured simply by testing that the preferred client configuration works as expected while remaining compatible with your existing applications and processes. Side-by-side evaluations are optional.

For step-by-step instructions to walk you through the installation and selection of features, see Chapter 3, “Introduction to Windows 95 Setup,” and Chapter 4, “Network Setup.”

Lab-Test the Installation

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Before running Windows 95 Setup, ensure that the appropriate network taps are working, power supplies are available, and so on. |  |  |  |
| 2: Make sure that the computer meets your standards and the Windows 95 minimum standards for operation — at least a 4 megabyte 386SX or better. If not, perform the hardware upgrades now. |  |  |  |
| 3: Defragment the hard disk and do a virus scan. Create and copy an MSD report to a floppy disk. |  |  |  |

Lab-Test the Installation, continued

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 4: Back up and verify key data and configuration files such as *.GRP, *.INI, AUTOTEXEC.BAT, and CONFIG.SYS and data files. |  |  |  |
| 5: Ensure that your current client configuration works properly on the test computers. |  |  |  |
| 6: Install Windows 95 on the test computer in the lab, using your preferred client configuration. |  |  |  |
| 7: Test the installation: · Can you connect and browse the network? · Can you print both locally and across the network? · Can you open, run, and close applications locally and on the network? · Can you shut down successfully? |  |  |  |
| 7a: (optional) If you have several test computers, compare your old client configuration under Windows 3.x and your new preferred configuration. How do the two compare in terms of the following: · Functionality for both administering the computer and using it for common tasks? · Performance for local disk and network actions? · Discoverability and ease of use for common tasks? · Stability of the two systems under stress? · Compatibility with applications and hardware? |  |  |  |

Lab-Test the Installation, continued

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 8: If the specified client configuration did not work as expected, modify and document the differences until a working preferred client configuration is installed. |  |  |  |
| 9: Perform a complete restoration of operating system files and system capabilities for your old client configuration on a computer running Windows 95 with the new client configuration. |  |  |  |
| 10: Evaluate the restoration process for problems. Document the process and modifications made for your system. |  |  |  |
| 11: Install the preferred configuration on a wider variety of hardware, with your team assisting in performing the installations. |  |  |  |

# V. 	Evaluate and Plan the Installation Process

Now that you have a thorough understanding of the functionality of Windows 95 on your preferred client configuration, it is time to plan the rollout to a pilot test case. This involves creating an automated installation process, planning the logistics of a pilot test, and creating a training plan for users.

Automating the installation is a key step in reducing the cost of migration. If you create a batch script with predetermined answers for installation questions, the installation process can run unprompted until completion. Further, you will want to use a method to “push” the installation from the server, so that you can install Windows 95 on an individual PC without ever touching the computer. The automation work is done in the lab.

The planning for the pilot test is a paper exercise and involves assessing how you will schedule, communicate, conduct, and support the pilot installation. Working through the logistics in the pilot test is key to a smooth rollout. You’ll also want to develop a end training plan that precedes the pilot test so that your users are trained and ready to use Windows 95 before it arrives on their desks.

Evaluate and Plan the Installation Process

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Use Network Setup to install Windows 95 source files on a server. Assume your client configuration, including whether you will run a shared copy of Windows 95 from the server, or run Windows 95 locally on the client computer. This includes the following steps: · Set up the distribution server · Set up the client from the network See Chapter 4, “Network Setup,” for step-by-step instructions. Document any changes to this process. |  |  |  |
| 2: Create and test an automated installation by creating a batch script to answer Setup settings requests. Document the key parts of the batch script that vary by installation. |  |  |  |

Evaluate and Plan the Installation Process,  continued

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 3: Determine and test how you will push the installation from the server without having to touch the client computers. (See Chapter 4, “Network Setup.”) This can involve a variety of options: · Modifying logon scripts on the server · Using a management software tool such as Microsoft System Management Server · Sending an embedded link via to the server by electronic mail and Windows 95 Setup Document the process for the rest of the implementation team. |  |  |  |
| 4: Evaluate the Windows 95 installation process for opportunities to upgrade or improve your organization’s technology infrastructure. For example, a systems management software tool can help you administer computers on the network more easily, and it can help with the push installation process. |  |  |  |
| 5: Document the logistics of the pilot installation. This includes the total time for installation, purchase of new software or tools, selection of the pilot group, and scheduling of specific installations. |  |  |  |

Evaluate and Plan the Installation Process,  continued

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 6: Put together a memo for your users which clearly explains how the installation process will affect their daily work schedule and the differences they will see once the installation is completed. |  |  |  |
| 7: Put a support plan in place for the pilot group. This includes a contact name and phone number for assistance, and a short list of the top questions and answers, and troubleshooting tips. |  |  |  |
| 8: Put together or hire a third party to provide a user training course. Windows 95 comes with several tutorials that you can use to jump-start your training efforts. |  |  |  |
| 9: Set up the lab or classroom with computers for hands-on training. |  |  |  |
| 10: Put together a training script that covers the computer’s basics and your company’s specific applications. |  |  |  |
| 11: Edit the Windows 95 Help file (if appropriate) to include any company-specific information. You’ll want to do this again after the pilot test is completed. |  |  |  |

# VI.	Pilot-Test the Installation

If you did a good job during the previous phase in planning the installation, conducting the actual pilot test should be straight forward. The key goals of the pilot program are to test your installation plan on a limited basis in real user scenarios to determine the problems that will hinder or slow the deployment process. You can then determin what resources you’ll require for the formal rollout, and accurately gauge the impact on the company of the move to Windows 95. Also, the pilot test will set the tone for the rest of the deployment process, and if done successfully, will help you obtain the appropriate cooperation and excitement to make the other installations run smoothly.

Pilot-Test the Installation

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Select a pilot group that is willing and has the time to handle the installation process. |  |  |  |
| 2: Train the users. |  |  |  |
| 3: Perform the installation in the same manner that you expect to install Windows 95 throughout the company. |  |  |  |
| 4: Have your technicians on-site for the initial installations to document the process and problems and to support the users. Have other technicians time and measure all phases of the installation process. |  |  |  |
| 5: Ensure that all systems are “up and running” as expected. Document areas in which the installation, training, or support can be improved. |  |  |  |
| 6: Survey members of the pilot group about their satisfaction with the installation process and take feedback on what could have been done better. |  |  |  |
| 7: Continue to monitor the pilot installation for a week to ensure that everything continues to run smoothly. |  |  |  |
| 8: If the pilot test did not run smoothly or user feedback was poor, conduct additional pilot installations until the process works well. |  |  |  |

# VII.	Create the Rollout Plan

The creation of the formal rollout plan is the final step in organizing and planning the deployment process. This involves setting the goals for the timing and scope of the installation process company-wide, and updating the company’s related policies and standards.

By projecting the results of the pilot test to your entire network, you can determine the time and resources required to meet your goals for moving to Windows 95. You may need to budget these resources and obtain approval before moving forward. After you have approval, you’ll want to proceed with hiring the extended implementation team and purchasing any additional tools or software needed to conduct the installation.

Create the Rollout Plan

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Determine your rollout goals — specifically the number of computers where you will install Windows 95 and the time expected to complete. |  |  |  |
| 2: Budget the resources for personnel and tools required to meet your goals. |  |  |  |
| 3: If necessary, present and obtain approval for the resources and the rollout process |  |  |  |
| 4: Hire and train the extended implementation team and purchase any additional software or tools needed. |  |  |  |
| 5: Update the company’s hardware and software standards lists. |  |  |  |
| 6: Update the company’s policies and practices manuals or guidelines for use of the PC and network. |  |  |  |

Create the Rollout Plan,  continued

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 7: Notify your users that the standards and policies lists will be enforced prior to the installation and to clean their systems and bring them up to compliance. |  |  |  |
| 8: If appropriate, edit the Windows 95 Help file to add company-specific help for line-of-business applications, and to remove unwanted information about the capabilities you plan to disable in Windows 95. |  |  |  |
| 9: Create a registration template or worksheet that lists the specific configurations and use of each computer. Be sure to leave room to document any problems or deficiencies with the system that require further attention. |  |  |  |
| 10: Post the updated registration file on a central network location. |  |  |  |

# VIII.		Conduct the Installation

Having thoroughly pilot-tested and documented the installation, training, and support process, you should be ready to roll out the installation to the rest of the company. This chapter has provided a quick overview of the issues in deploying Windows 95. The next chapter, “Planning the Details,” presents the detailed discussion for each of the deployment phases, including examples and descriptions.

The rest of the Windows 95 Resource Kit provides specific how-to steps for conducting the actual installation, maintenance, and operation of Windows 95 and background technical information to help you support it.

Conduct the Installation

| Task | Team | Start Week | Duration |
| --- | --- | --- | --- |
| 1: Set up the distribution servers by using the NETSETUP.EXE program and configuring the policy file. |  |  |  |
| 2: Customize the server installation by adding or removing the appropriate files such as adding the MSBATCH.INF file. (For more information, See Chapter 2, “Planning the Details”) |  |  |  |
| 3: Notify the users of the upcoming installation. |  |  |  |
| 4: Train the users on Windows 95. |  |  |  |
| 5: If needed, upgrade the hardware on the client computers and remove any software not complying with company policy. |  |  |  |
| 6: If needed, back up the data and configuration on the client computer. |  |  |  |
| 7: If needed, run Scandisk and virus checks, and defragment the client hard disk. |  |  |  |
| 8: Ensure that the client computer is fully operational and the real-mode network, if present is running. |  |  |  |
| 9: Prepare the client computer for the push installation process: edit the logon script; run the management software; or send the executable for Setup in mail to the user. |  |  |  |
| 10: Initiate the installation by having the user logon, double-click on the executable, and so on. |  |  |  |

Chapter 2

This chapter is the second part of the Deployment Guide and contains details on the particular phases for rolling out Windows 95. If you are comfortable with the early planning phases of deployment, you can skip ahead to the section, “Specifying Your Preferred Client Configuration”.

Deployment Guide:  Planning the Details

I.       Reviewing the Product: The Details    2-2

@In This Chapter

II.     Assembling the Evaluation Team and Tools:  The Details    2-4

III.    Specifying Preferred Client Configurations: The Details    2-6

IV.    Lab-Testing the First Installation: The Details    2-12

V.     Evaluating and Planning the Installation Process: The Details    2-14

VI.    Pilot Testing the Installation: The Details    2-16

VII.  Creating the Rollout Plan: The Details    2-17

VIII. Conducting the Installation    2-18

# I.	Reviewing the Product: The Details

This is the first phase of the deployment process which entails reading about Windows 95 features and benefits to understand how they help you reduce your support costs and increase business profitability. If you are comfortable with this topic, you can move to section II “Assembling the Evaluation Team and Tools:  The Details.”

## Reading the Windows 95 Reviewer’s Guide

The Windows 95 Reviewer’s Guide is a 300-page document that provides information about Windows 95 features and functionality. This publication discusses the changes and enhancements made to the Microsoft Windows operating system that make Windows 95 easier to support and manage in a network environment.

For information on where to access the Reviewer’s Guide or any other Windows 95 information comment to the Microsoft WIN_NEWS forum at the following electronic locations:

On CompuServe®:		GO WINNEWS

On the Internet:			ftp://ftp.microsoft.com/PerOpSys/Win_News/Chicago

http://www.microsoft.com

On America Online®:	keyword WINNEWS

On Prodigy™:			jumpword WINNEWS

On GEnie™:				WINNEWS file area on Windows RTC

You can also subscribe to the Microsoft electronic newsletter WinNews. To subscribe, send electronic mail on the Internet to enews.microsoft.nwnet.com and include the words SUBSCRIBE WINNEWS in the text of the electronic message.

## Reviewing the Business Case for Windows 95

A number of industry analysts have already provided or are currently preparing economic models which measure the impact of upgrading an organization to Windows 95 in terms of migration costs, total cost of ownership, and productivity benefits.

To be provided: a summary of the business case information here and pointers to online locations of third-party studies and analyses of Windows 95, with respect to business profitability.

## Optional: Attending a Windows 95 Seminar for the Information Systems and Network Professional

Microsoft periodically sponsors seminars on products such as Windows 95 to provide information that can help with planning and deployment. As of this writing, we are currently planning seminars for the information systems professional which provide an overview of Windows 95 from a organization perspective. The seminar will include a demonstration and highlight key features such as system management, integrated network support (especially for NetWare or Windows NT networks), and security. The seminar will also show a live Windows 3.1 migration of a typical corporate client.

To sign up for the U.S. tour, call 1-800-685-0951.

To be provided: Seminar Dates and Locations

## Optional: Reading Inside Windows 95

Inside Windows 95 is a book published by Microsoft Press which describes the internal operation of Windows 95. The author, Adrian King, spent seven years in the Microsoft System Software Division, and wrote the book from an objective perspective, yet with an insider’s knowledge, while Windows 95 was under development. He explains the base system and the new user interface and offers new guidelines for application developers, along with tips on porting, multitasking, OLE, internationalization, color matching, device-independent bitmaps, and the printing subsystem. King also includes perspectives on why design decisions were made and how the design changed during development.

# II.	Assembling the Evaluation Team and Tools:  The Details

This phase involves gathering the resources to properly evaluate Windows 95.

## Assigning the Project Manager and Key Team Members

When setting up the evaluation team it is important to include a representative set of individuals who will be involved with the deployment process. This includes people from Corporate Support, Employee Training, the Corporate Standards Committee, and one of the Installation team members. You eventually will need to work with the Finance and Accounting group, but an individual from that group need not be on the evaluation team.

## Profiling Your Company’s Hardware and Software Inventory for Servers and Client Computers

Gathering this data inventory involves the use of additional software management tools to query computers on the network for their hardware and software configurations. You’ll need to survey a representative sample of your network to accurately simulate the organizational environment in the lab. Having done so will also help you make broad decisions about your organization infrastructure, such as the choice of protocol or default desktop configuration as it pertains to applications.

To be provided: A comprehensive example of the inventory survey process and tools to help conduct the survey. Also, a checklist of all of the hardware, software, drivers, user names, and configuration information, and so on, that you should audit to help specify your preferred client configuration.

## Securing a Testing Lab and Equipment

To effectively evaluate and test the Windows 95 installation process, you will need enough computers and space to test everything from installing Windows 95 source files on a server for your NetWare or Windows NT network, to configuring and optimizing your most basic client computer.

In addition, if your network environment includes the use of laptops which dial into the company, or if you use additional servers or mainframes for business data, you’ll want to ensure that the lab computers have full access to the network and an analog phone line.

It is important that you comprehensively test and implement all of the Windows 95 features with all of your business-specific applications in the lab before moving to the pilot test.

## Optional: Sending Team Members to a Microsoft Authorized Technical Education Center (ATEC)

To learn more about Microsoft Windows 95, call (800) SOLPROV for a referral to a local Microsoft Solution Provider Authorized Technical Education Center or call the Microsoft Fax Server at 800-727-3351 and request document # 10000256 for the location of the Authorized Academic Training Program (AATP) site nearest you. Microsoft ATECs and Microsoft AATPs offer Microsoft Official Curriculum delivered by Microsoft Certified Trainers to educate computer professionals on Microsoft technology.

Microsoft Official Curriculum for Microsoft Windows 95 currently includes: Supporting Microsoft Windows 95 (5 days) course and Self Study course material.

For other training information, see Appendix F, “Windows 95 Resource Directory.”

# III.		Specifying Preferred Client Configurations: The Details

This phase requires the most thought and analysis, as it involves determining your preferred client configurations. The approach taken in this chapter is to assume that you require the most functional and best-performing client software. Then you can review each of the key features of this ideal client and determine whether you need to use this feature or whether you require an alternative for compatibility reasons. Do this for each of your likely client configurations.

## Using a 32-bit Network Client

For best performance, the preferred network client is one that uses a 32-bit redirector for accessing servers. Windows 95 includes the 32-bit Microsoft Client for NetWare and Client for Microsoft Networks. Network vendors are also creating additional 32-bit redirectors. The benefits of using a 32-bit, protected-mode client include the following:

·	Uses no real-mode memory

·	Faster I/O across the network

·	More stable

·	Able to use more than one redirector at one time

·	Makes networking seamless in the Windows 95 user interface

The first two benefits are compelling enough to switch to a 32-bit network client. Another benefit of the newer redirectors is that you are able to run multiple network clients simultaneously, thus giving you access to servers for multiple networks without having to reload the operating system with a new network client.

The last point about seamless user interface integration refers to the ability to browse the server for multiple networks in Network Neighborhood, all in the same namespace. This means that your users can search for data by the name of the server and not have to worry about which type of network they are browsing.

You will not want to run a 32-bit client in the following cases:

·	Novell networks:

·	Running the following TSRs or applications: to be provided.

·	You do the following networking tasks: to be provided.

·

Microsoft Networks:

·	Running the following TSRs or applications: to be provided.

·	You do the following networking tasks: to be provided.

·	You are debugging a problem with the network.

As of this writing, all other networks require a real-mode client. HoweVer, you can run a protected-mode Windows 95 client such as Client for Windows Networks in conjunction witih a real-mode network client.

## Using a 32-bit Protocol

If you select a 32-bit client, then by default Windows 95 will also set up a 32-bit protocol. Even if you are running a real-mode client such as the Novell 3.x workstation shell (NETX) with a real-mode implementation of IPX/SPX to access NetWare servers, you can still load the 32-bit version of the IPX/SPX-compatible protocol written by Microsoft. The benefits of doing this are that for any other network communications to non-NetWare servers, such as other computers running Windows 95 in a peer environment, or to servers on a Windows NT network, the computer operates in 32-bit protected mode. Again, this means faster performance and increased stability without any real-mode memory loss.

In addition, for protocols such as TCP/IP, the Microsoft 32-bit version enables additional functionality such as the ability to use DHCP and WINS servers which dynamically set the IP addresses and resolve computer names for client computers on the network. Each protocol has a number of benefits that are discussed in Chapter 7, “Network Technical Issues.” If you are new to networking, this chapter also has a discussion of how to choose the right protocol for your network.

## Using the Latest Network Adapter Card Drivers

For best performance you will want to use the latest network adapter card drivers available. These should be NDIS 3.1-compatible with Plug and Play capabilities. Such drivers take up no real-mode memory and can be loaded or unloaded dynamically as required.

The only instances in which you wouldn’t use the latest drivers are :

·	The newest driver isn’t available for your network adapter card.

·	Your site uses ODI cards and drivers.

·	To be provided: other causes for incompatibility or conflict.

## Using Long Filenames

The long-filename capabilities of Windows 95 allow users to give files and directories names that are longer than the 8.3-character limitation of the file allocation table (FAT) file system. The Windows 95 VFAT file system can use longer filenames while automatically providing 8.3-filenames when needed for compatibility with other operating systems. Application vendors are revising their applications to work with long filenames — such applications are distinguished by the Windows 95 logo — and thus provide great interoperability across the PC platform.

Nonetheless, there are issues that you will want to work through in the interim to support a mixed environment. These are discussed in Chapter 15, “Disks and File Systems.” Reasons that you would not or could not use long filenames include:

·	You configured the computer during Windows 95 Setup not to use long filenames.

·	You don’t have a plan in place to manage the transition between computers running Windows 95 and other computers.

## Optional: Using Recommended Features

### Using System Policies

To control the access and security on each client computer you will want to use system policies. System policies allow you to control or disable a variety of Windows 95 features and capabilities that users may accidentally — or deliberately— use to access information or damage data on their systems. For example, if you want to disable the ability to use peer resource sharing services or the ability to use the command prompt, system policies make it easy to do this from a central location for a large number of users.

To be provided: Worksheet to walk you through the variety of options you may control with System Policies.

Enabling policies is primarily done at the server side so it does not involve the client computer. In general, the server configuration can be done after Windows 95 is installed, but there are a few cases in which adding support for additional capabilities — such as group support or a non-standard server path for updates — requires some configuration on the client computer. For information on how to use system policies, see Chapter 12, “System Management.”

There isn’t a comparable substitute for system policies, though you can disable certain capabilities by actually deleting the appropriate system files. This is not recommended.

If you choose not to use policies, no action needs to be taken.

### Using User Profiles

User profiles are similar to to system policies. Profiles enable a user to use custom desktop settings that are available each time he or she logs into a computer. Multiple users on a single computer can customize their own desktops and load them at logon time. Conversely, a single user can move between computers using the same profile by storing the profile on the server. An administrator can also take advantage of profiles to require that a single standard desktop get loaded each time any user logs on. The abilitiy to change profile settings can be controlled by the administrator. For information on how to use user profiles, see Chapter 12, “System Management.”

User profiles are not needed when only one person uses the computer or when a custom desktop adds no value. By not enabling user profiles, the logon process is shortened, because the system does not need to check for the Profile file and then load it.

### Enabling Remote Administration

To remotely administer a computer’s Registry or policies you must enable this capability by installing the network services called Microsoft Remote Registry Service and the Microsoft Network Monitor Agent on the client computer. The remote service allows you to conduct a variety of tasks remotely over the network such as administer the file system, share or unshare directories, or query and make changes to the Registry. If you plan to do any of these tasks, you’ll definitely want to enable this feature.

You should not enable remote administration if you don’t need these services, because doing so needlessly runs extra processes on the network. These extra remote services can then theoretically be used by someone on the network — given the knowledge of the appropriate password — to access information on your clients. Windows 95, nonetheless, comes with security capabilities to protect against unapproved access. For more information, see Chapter 12, “System Management.”

### Using Push Installations for Windows 95 Setup

You need to understand and plan in advance how the push installation process will work for a given computer. There are a number of alternatives for remotely initiating the installation, ranging from editing the client’s logon script, to sending a link in mail to the server and Windows 95 Setup SETUP.EXE file. You will want to consider how you push the installation for each computer and ensure that the clients are configured to support this process.

For organizations with 50 or more computers, being physically present to install each client computer is not a viable option because of the cost. In that case, you may need to turn to a third-party software solution such as Microsoft Systems Management Server. Other software tools may require some software on the client side and thus you will need to factor this into the installation.

For more information about planning and using push installations, see Chapter 4, “Network Setup.”

### Using Batch Scripts for Windows 95 Setup

Batch scripts allow you to predefine answers to Windows 95 Setup during installations. Batch scripts go hand-in-hand with push installations to completely automate the installation process. The choice to use a batch script is very straightforward. If you need to conduct a similar installation more than five times, you should use a batch script. You need to begin planning for batch scripts and push installations at this point of the preferred-client specification phase, to ensure that you document each feature needed, so you can automate the selection of these features. For more information, see Chapter 4, “Network Setup.”

### Using Peer Resource Sharing Services

The peer resource sharing capability in Windows 95 allows your client computers to share files and data directly from a local PC, as opposed to having to use a central server. Because of this capability, peer sharing may reduce the amount of network traffic and server disk space required, because you are leveraging the power of each individual computer. Choosing to use peer services in Windows 95 is a relatively easy process during installation. It also is quite secure if you have user accounts on a server for a Windows NT or NetWare network which can support user-level security from the server. If you don’t have servers to provide security validation or don’t want to use user-level security, you can use share-level security, which relies on each individual to implement security and a password scheme on the local computer. Share-level security is set on a directory-by-directory basis.

If you do not want to use peer services, and, in addition, want to disable the capability permanently from each of your clients, you can do so by selecting the appropriate option in System Policies.

## Optional: Using Other Features

### Using the Microsoft Exchange Mail Capability

The new Microsoft Exchange application in Windows 95 provides a single place to manage all messaging information, by implementing a single Inbox for electonic mail, faxes, and other messages. In addition, Windows 95 comes with a complete small-business mail system — that is, a mail client and post office — that allows users to exchange electronic mail through a single post office. This mail client integrates well into Microsoft Mail Servers and the post office can be upgraded to provide an enterprise mail system.

You can also use a variety of other mail or messaging systems through Microsoft Exchange as long as they use a MAPI 1.0 driver. A number of these drivers currently under development by other vendors include access to CompuServe, the Internet, and Novell MHS systems. If you have an existing mail system and don’t have a MAPI 1.0 driver, you can continue to use your existing mail system and not install the Microsoft Exchange Mail capability. In this case, you’d install Microsoft Exchange only if you wanted to use other features such as the At Work Fax capability. Microsoft Exchange is used for containing your incoming faxes when using the At Work Fax capability.

For more information, see Chapter 19, “Microsoft Exchange and Mail”.

### Configuring the Windows 3.1 User Interface

To be provided:  Detail on how to ease the migration to the new user interface.

### Assessing Other Features

Windows 95 comes with a host of new features which enable you to take advantage of new hardware and capabilities. These include:

·	Remote dial-up capabilities

·	At Work Fax

·	Disk management tools

·	Applications for common functions like text editing

You will want to manually install some or all of these during Setup. For more information, see the Windows 95 Reviewer’s Guide.

To be provided: Details for implementing each particular feature.

# IV.	Lab-Testing the First Installation: The Details

This phase in the deployment process involves four significant efforts. These are: Preparing the Site, Conducting the Installation, Testing the Installation, and Restoring the System.

## Preparing the Site

Preparing the site involves ensuring that the location of each computer, the computer itself, the hard disk, and the data are all ready for Windows 95 to be installed. In terms of the physical site, you’ll want to ensure that you have the appropriate network taps to connect fully to the network. You may require a power supply and surge protector, depending on the number of computers. And you’ll want to have evaluated any issues with regards to overheating or frequency distortion from the location.

In terms of the PC itself, you’ll need to ensure that it has the appropriate hard disk space, RAM (at least 4 MB, but 8MB is recommended), and processor (386SX or better, a 386DX or better is recommended) to run Windows 95. For the requirements for running a shared copy of Windows 95 from a server, see Chapter 4, “Network Setup.”

In addition, you’ll want to run a virus detection, disk scan, and a defragmentation program on the computer to ensure that no problems are lurking on the computer before installation. Although the computer may appear to be operating properly, software upgrades often uncover hardware or software problems, because of the way they read and write data to the hard disk. Checking the computer before installing Windows 95 will help you better focus on issues related to installation.

Lastly, when preparing the site, you’ll want to back up key data and configuration files for the system, in case the installation fails or you need to revert to the old system for some reason. This includes backing up *.INIs, such as WIN.INI and SYSTEM.INI, *.GRPs, AUTOEXEC.BAT, and CONFIG.SYS and all key data files. You also should create a Microsoft Diagnostics (MSD) report and copy it to a floppy disk by running the MSD.EXE on the hard disk. You’ll want to consider using a standardized backup program, instead of copying the files by hand, if you have a need for an automated restore process.

## Conducting the Installation

Setting up Windows 95 for the first time is fairly straightforward and requires only a minor amount of extra effort. This includes using Part 2, “Installation and Networking,” in the Windows 95 Resource Kit to help you install and configure Windows 95 correctly. Chapter 4, “Network Setup,” includes instructions on how to automate the installation process using batch scripts. You’ll want to follow along and check off the appropriate batch entries or each option during Windows 95 Setup.

## Testing the Installation

After you’ve set up a computer with Windows 95, you’ll need to run a variety of tests to ensure that it runs correctly on your system and that you can still perform all of your usual tasks. You probably have your own testing methodology, but if not, you’ll want to ensure that you can perform at least the following tasks:

·	You can connect to and browse the network.

·	You can set up a printer and print both locally and on the network.

·	You can open, run, and close applications both from the client and the server.

·	You can shut down completely.

In addition to ensuring that the preferred client configuration works as expected, you may also want to conduct additional testing between the optional software features and components in Windows 95. This can help you determine whether you are running Windows 95 optimally. For this kind of testing, you’ll want to conduct side-by-side evaluations on two computers, changing each feature individually, to determine the following:

·	Performance in terms of responsiveness and throughput

·	Ease of use and discoverability

·	Stability

·	Compatibility

·	Functionality

One example of the type of evaluation was referred to previously when choosing the network client software or redirector for Novell NetWare. For performance evaluation, you may want to run the following network performance tests:

·	To be provided.

For ease of use, you’ll want to conduct several common tasks such as connecting to the network, administering a remote NetWare server, and so on. Similarly, you’ll want to run any business specific NetWare applications with the newer client to ensure that they run compatibly. Stability concerns should show through on your testing of the other features, but the following test can be use to do a more rigorous evaluation.

·	To be provided.

For information about functionality, you’ll want to read the Reviewer’s Guide and as the appropriate chapter in the Windows 95 Resource Kit to try out the functionality of the newer client.

## Testing the Restore Process

Having thoroughly tested the preferred client, you’ll want to perform a complete restore of one of the test computers to the previous client configuration to understand and document the process. The degree to which you need to test and restore the computer depends on the tools at your disposal. Chapter 5, “Setup Technical Issues,” documents how to restore the system manually.

# V.		Evaluating and Planning the Installation Process: The Details

This phase involves three major efforts: automating the installation, documenting the logisitics of the pilot installation, and assembling the user training plan. These efforts are a mixture of planning and lab-testing work.

## Automating the Installation

Automating the installation involves creating a batch script, setting up Windows 95 correctly on the server, and creating a push installation process.

With a batch script you can perform a hands-free installation, so that the user need not answer any dialogs or even touch the computer during Windowss 95 Setup.

Installing Windows 95 source files on the server is a separate and distinct process from the client setup program (SETUP.EXE) that you ran in the initial lab installation. Setting up the server requires the Network Setup program (NETSETUP.EXE) from the Windows 95 compact disc.

When you run Network Setup, you also create a default setup script, and you can specify whether the Windows 95 source files on the server will be used to set up Windows 95 to run locally from a standalone computer or to run a shared copy from the server for client computers that require a shared installation.

In addition, you may want to manually add other files to the shared directory on the server, such as custom bitmaps for screens, or a predefined WKGRP.INI file for workgroup organization, so that client computers are fully configured when Windows 95 is installed.

Creating a push installation process involves doing some final work on the server,  such as editing the logon script for the user, or sending a link in mail to the Windows 95 Setup executable file, so that the user only needs to sign in or double-click on an icon to start the installation. Systems management software such as Microsoft System Managment Server can also be used to start the installation centrally.

For more information, see Chapter 4, “Network Setup.”

## Documenting the Logistics of a Pilot Installation

This involves choosing the pilot group, determining the length and process of the group installation, and developing the support and communication plans.

Even though you are just testing the installation process, the first pilot sets the tone and establishes an example of the deployment, so it is important that you are “buttoned up” on all aspects of the rollout. You’ll need to determine the overall time it will take to install the pilot, the personnel and tools to facilitate the process, and the schedule. Determining the time of installation should be on an individual PC basis and is key for scheduling the downtime for each user. In turn, to meet your timing goals to complete the pilot installation, you will need to staff your implementation team with the appropriate personnel and with any additional tools, such as management or debugging software, that can automate the installation.

In addition, it’s important you choose a group that is interested in and capable of being the first test case. Choosing a pilot group that is right-at-deadline on a project, or one that is traditionally a laggard in adopting new technology only increases the difficulty of the first installation.

Another part of making the deployment process more acceptable to the users is formulating a communication plan. The communication can be in a number of forms — video, memo, company meeting — but must contain several key elements You should clearly describe, and, if possible, demonstrate the user benefits of moving to Windows 95 as part of the introduction to Windows 95. Similarly, you should communicate the overall plan and process by which you will move each group or department to Windows 95. This makes it easier for your users to plan and accept the move to Windows 95 as part of their schedules.

## Assembling the End-User Training and Support Plan

The final aspect in planning the installation process is creating a training and support plan. The pilot stage tests not only the installation process, but the training process as well. Consequently, you will need to find the internal resources, such as a training lab, computers, and an instructor, or hire an outside firm to help put together and test the training plan. You should train the users just before the installation so that they can immediately put to use their knowledge of Windows 95. Thus, the pilot rollout starts first in the training lab.

Providing effective support for Windows 95 also requires up-front planning, in that you will need to be ready to go on the same day you begin performing Windows 95 installations. Your support plan should include some of your best technicians, dedicated solely to the pilot group for the first few weeks. They should carry beepers or be near a phone in case they need to visit the client computer early in the process. In many ways, the completeness of your support will be the biggest indicator to the rest of the company of the quality of the forthcoming rollout process.

You can also provide additional tools for both training and support to help users help themselves. Some of these include editing the Windows 95 Help System to provide company-specific help on applications or features that you know will raise issues with users. To be provided: Instructions on how to edit the Help File.

# VI.		Pilot-Testing the Installation: The Details

Having done the appropriate planning in the previous phase, the pilot installation should run smoothly — at least, according to plan. The key areas to focus on when conducting the actual installation are: simulating the likely installation process; testing the capabilities and performance of the system; and surveying and adjusting to user feedback.

## Simulating the Installation Process

To get an accurate assessment of how the real installation process will rollout, you’ll want to run the pilot just as you would run a fire drill. This means that you set a timing goal for the installation process and stick to the predefined schedule. By running the pilot in this fashion you will uncover problems with either your schedule or installation process that you will need to fix.

## Testing Windows 95 Capabilities and Performance

Inspite of running the pilot test under a real-world scenario you’ll want to have an additional number of technicians test and measure the installation. Specifically, these individuals will measure the time per installation, handle problems that arise, and highlight areas for improvement or automation. Additionally, once Windows 95 is installed, they will test all of the capabilities, such as the remote administration features for systems management, to ensure that everything is working properly. They also will monitor the client computers for performance, stability and functionality, to highlight any inconsistencies with the lab configuration.

To be provided: actual testing steps.

## Surveying and Adjusting Based on User Feedback

The final part of the pilot test involves surveying the users. You’ll want to understand their satisfaction and proficiency with the new installation and the level of training and support provided. You’ll want to test their proficiency by having them execute a few common tasks or use several of the new features in Windows 95, for example, to register their survey results on the server.

# VII.	Creating the Rollout Plan: The Details

The official rollout plan is an extension of the pilot planning process which includes documenting, budgeting, and executing the logistics. In addition, you’ll want to update the Policies and Practices Guidelines and create the Registration Template.

## Documenting, Budgeting, and Carrying Out the Logistics

In a manner similar to the pilot process, you will need to estimate the length and scope of the overall installation process and thus the tools to meet your deadlines. Additionally, you may need to formally budget and present this information to management for approval. Your budget should include the costs for personnel and additional resources, such as systems management software, that you will purchase to facilitate the installation. It is important that you hire experienced and qualified individuals for the team, because you’ll end up spending more money having to correct a bad installation versus doing it right the first time. Also be sure to train them extensively before getting started.

In terms of execution, this is the stage in which you complete your training, communications, and staffing plans for the rollout. Each of these areas should be appropriately specified and ready to go before starting the actual rollout.

## Updating the Policies and Practices Guidelines

At this phase you also need to update any formal company policy with regards to using the network and the PC. This involves making changes to common practices such as the password length and expiration requirements, and the level of approval needed to obtain remote dial-up privileges.

In addition, you will want to update the Corporate Standards lists for software usage so that you can bring all computers up to compliance during the installation process. Since Windows 95 enables a host of new 32-bit applications and Plug and Play-compliant hardware, you’ll want to add these new products to the list, and delete their older counterparts.

## Creating the Registration Template

To keep up with the progress of the rollout and document any areas of additional assistance, you’ll want to set up a central registration template or database on one of your servers. Your implementation team should then register each computer and user when Windows 95 is installed, noting any additional features or capabilities that need upgrading. In this fashion you can track problematic computers that may need to be upgraded and measure your progress on the installation against original objectives.

# VIII.		Conducting the Installation

The basic steps for the conducting the installation have either been discussed previously or are covered in detail in Part 2, “Installation and Networking,” in the Windows 95 Resource Kit. If you have followed the deployment guide closely, you should be well prepared to work through these chapters.

To be provided: Checklist for conducting the installation.